## NRC
NRC_ID | Register | Ref_Task | Description | Area | Trade | ATA | Status | Standard | Total | MH_Changed
QZL0010 | B-HNU | 777-BM-CONTROL-CARD-01 | TOWING A/C FOR MAINTENANCE/OPERATIONAL NEEDS | FUS | AE | 09 | WIP | N | 50.01 | 0
QZL0028 | B-HNU |  | AS PER B-HNU E-TECH LOG OPEN TL ENTRIES TL4332 - MSG APPEARED WHEN RIGHT WX SYS SELECTED. | CAB | AV | 46 | OPEN | N | 2 | 1.99
QZL0036 | B-HNU | 777-5000-10-025-01 | PLS REMOVE PED 1 2 4 5 HINGE COVER FOR EPAS BATTERIES REMOVE | CAB | AI | 5212 | COMP | N | 4 | 0
QZL0044 | B-HNU | 777-5000-10-026-01-1 | AIRCRAFT REFUEL FOR PARKING | F/T | AE | 28 | COMP | N | 5 | 0
QZL0051 | B-HNU | SWC-28778-01-01 | ZONE B SEATS 39F 40B 43C 45A 39D 46A 48A 48B 50A 50B 50C 52A 52C 52F 49D 48E 47D 47E 46D 45F 44D 44E 41D 41F 40K 43J 43K 44H 45K 46H 46K 47H 47K 50H 50J 50K 51J 51K 52J 52K MONITOR TOUCHSCREEN FOUND MALFUNCTION | CAB | AV | 2332 | WIP | N | 100 | 1.99
QZL0069 | B-HNU | SWC-28778-01-01 | ZONE C SEAT 56B 57C 59A 59B 61A 61B 65C 66B 67B 66D 64D 64F 63D 62F 62D 61F 59F 57E 57G 56E 54G 55K 56J 59H 59J 61J 61H 62H64H 64K MONITOR TOUCHSCREEN FOUND MALFUNCTION | CAB | AV | 2332 | WIP | N | 80 | -20.01
QZL0070 | B-HNU | SWC-28778-01-01 | ZONE C SEAT 56B 57C 59A 59B 61A 61B 65C 66B 67B 66D 64D 64F 63D 62F 62D 61F 59F 57E 57G 56E 54G 55K 56J 59H 59J 61J 61H 62H64H 64K MONITOR TOUCHSCREEN FOUND MALFUNCTION | CAB | AV | 2332 | WIP | N | 50 | 50
QZL0071 | B-HNU | SWC-28778-01-01 | ZONE C SEAT 56B 57C 59A 59B 61A 61B 65C 66B 67B 66D 64D 64F 63D 62F 62D 61F 59F 57E 57G 56E 54G 55K 56J 59H 59J 61J 61H 62H64H 64K MONITOR TOUCHSCREEN FOUND MALFUNCTION | CAB | AV | 2332 | WIP | N | 12 | 0

## Subtask
Register | Proj_Id | Class | Sheet | Item_No | Description | Jsn | Mhr | Trade
B-HNU | QZ | NRC | 1C | 1 | TOWING A/C FROM 1 BAY O/S TO 12 BAY O/S AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 2C | 2 | TOWING A/C FROM 12 BAY O/S TO 10 BAY O/S FOR REFUEL AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 2C | 3 | TOWING A/C FROM 10 BAY O/S TO 12 BAY O/S AFT REFUEL AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 3C | 4 | TOWING A/C FROM 12 BAY O/S TO 11 BAY O/S AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 4C | 5 | TOWING A/C FROM 11 BAY O/S TO H6-1 AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 5C | 6 | TOWING A/C FROM H6-1 TO BETWEEN H1 & H3 O/S AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 6C | 7 | TOWING A/C FROM H1 & H3 O/S TO BAY 12 O/S AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 6C | 8 | TOWING A/C HANGAR IN. AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 7C | 9 | TOWING A/C TO ENGINE RUN POSITION OUTSIDE OF HANGAR 6. AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 8C | 10 | TOWING A/C FROM H 6 OUTSIDE TO BAY10 AS PER AMM 09-11-00-580-801 REV 05MAY2023 | L001 | 5 | AE
B-HNU | QZ | NRC | 1C | 1 | PLEASE REMOVE SEAT CUSHION AS PER CMM 25-27-63 REV 17 08 OCT 21 | L005 | 8 | SS
B-HNU | QZ | NRC | 1C | 2 | REMOVE THE DEFECTIVE MONITOR AND RETURN TO STORE FOR SHOP REPAIR AS PER CMM 25-27-63 REV 17 08 OCT 21 | L005 | 40 | AV
B-HNU | QZ | NRC | 1C | 3 | INSTALL NEW MONITOR AND PERFORM IFE INDIVIDUAL SYSTEM TEST AS PER CMM 25-27-63 REV 17 08 OCT 21 | L005 | 48 | AV
B-HNU | QZ | NRC | 1C | 4 | INSTALL SEAT CUSHION AS PER CMM 25-27-63 REV 17 08 OCT 21 | L005 | 10 | SS
B-HNU | QZ | NRC | 1C | 1 | PLEASE REMOVE SEAT CUSHION AS PER CMM 25-27-63 REV 17 08 OCT 21 | L006 | 6 | SS
B-HNU | QZ | NRC | 1C | 2 | REMOVE THE DEFECTIVE MONITOR AND RETURN TO STORE FOR SHOP REPAIR AS PER CMM 25-27-63 REV 17 08 OCT 21 | L006 | 30 | AV
B-HNU | QZ | NRC | 1C | 3 | INSTALL NEW MONITOR AND PERFORM IFE INDIVIDUAL SYSTEM TEST AS PER CMM 25-27-63 REV 17 08 OCT 21 | L006 | 36 | AV
B-HNU | QZ | NRC | 1C | 4 | INSTALL SEAT CUSHION AS PER CMM 25-27-63 REV 17 08 OCT 21 | L006 | 8 | SS
B-HNU | QZ | NRC | 1C | 1 | REMOVE THE POSITION 54H DEFECTIVE ARM MONITOR AND RETURN TO STORE FOR SHOP REPAIR AS PER CMM 25-27-63 REV 17 08 OCT 21 | L007 | 1 | AV