## BMS_Project
proj_id | cust_id | ac_type | ac_regn | check_type | ac_iata_code
VT | CX | 777 | B-KQX | 3C | 777

## Detail
job_no | orig_cust_ref_no | defect_desc | zone_no | stage | work_area | dock_trade | ata_no | est_mhr | ttl_est_mhr | job_status | Remark
VTL0018 | 777-900001-01-1-01 | C/OUT THE A/C TOWING | 700 | NRP | LDG | AE | 09 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL0026 | TA28000201 | PERFORM A/C DEFUEL FOR C-CHK INPUT. | 500 | NRR | F/T | AE | 2800 | 0 | 0 | COMP | For maintenance only, No charge to CX
VTL0034 | TA28000201 | PERFORM ALL FUEL TANKS SUMP DRAIN FOR C-CHK INPUT. | 500 | NRR | F/T | AE | 2800 | 0 | 0 | COMP | For maintenance only, No charge to CX
VTL0042 | 777-32-130-00-01 | LIFT THE A/C FOR MAINTENANCE REF TO XMN TASK CARD: TA07000101-BOE | 700 | NRR | LDG | AE | 32 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL0059 | 777-53-920-00-01 | CABIN OHAR ENTRANCE AFTER VERTICAL RUB STRIP FOUND SCRATCH | 200 | NRR | CAB | AI | 2500 | 3 | 3 | OPEN
VTL0067 | 777-53-920-00-01 | CABIN OHAR ENTRANCE FWD&AFTER KICK STRIP FOUND DETACH | 200 | NRR | CAB | AI | 2500 | 2 | 2 | WIP
VTL0075 |  | MAINTENANCE MESSAGE 24-28801 BPCU HAS NO OUTPUT ON ANY BUS | 100 | SIA | LWR | AV | 2400 | 0.01 | 11.01 | WIP
VTL0083 | 777-C257100-01-07-01 | CABIN G1C GLY SINK DRAIN AND WASTE CHUTE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 1 | 1 | COMP
VTL0091 | 777-C257100-01-07-01 | CABIN G1C GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0109 | 777-C257100-01-07-01 | CABIN G1L GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0117 | 777-C257100-01-07-01 | CABIN G2 GLY SINK DRAIN SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 1 | 1 | COMP
VTL0125 | 777-C257100-01-07-01 | CABIN G2 GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0133 | 777-C257100-01-07-01 | CABIN G3 GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0141 | 777-C257100-01-07-01 | CABIN G4 GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0158 | 777-C257100-01-07-01 | CABIN G5 GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0166 | 777-C257100-01-07-01 | CABIN G4R GLY SINK DRAIN AND WASTE CHUTE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 1 | 1 | COMP
VTL0174 | 777-C257100-01-07-01 | CABIN G4R GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0182 | 777-C257100-01-07-01 | CABIN G6 GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0190 | 777-C257100-01-07-01 | CABIN G7 GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 2 | 2 | COMP
VTL0208 | 777-C257100-01-07-01 | CABIN G6 GLY SINK DRAIN AND WASTE CHUTE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 1 | 1 | COMP
VTL0216 | 777-C257100-01-07-01 | CABIN G7 GLY SINK DRAIN AND WASTE CHUTE SEALANT FOUND DETACH | 200 | NRP | CAB | AI | 2530 | 1 | 1 | COMP
VTL0224 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC001: BOTH ENGINE OIL TYPE ON THE L ENGINE HAS BEEN CHANGED FROM MOBIL JET II TO ETO 2197 POST ACCOMPLISHMENT OF AEO-25935. | 400 | LOG | ENG | AE | 79 | 0.01 | 0.01 | COMP
VTL0232 | 777-C252500-01-06-01 | CABIN PEY/EY LH CLASS DIVIDER BABY BASSINET SAFETY STRAP FOUND DIRTY | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL0240 | 777-C252500-01-06-01 | CABIN F LAV AFTER BABY BASSINET SAFETY STRAP FOUND DIRTY | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL0257 | 777-52-195-00-01 | AFT CGO FWD & AFT ROTARY ACTUATOR FOUND NOISE DURING CLOSE | 800 | NRR | LWR | AI | 5200 | 0.01 | 17.01 | WIP
VTL0265 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC002: THIS AIRCARFT IS INSTALLED WITH 2 CREW OXYGEN CYLINDERS AEO-26231 OXYGEN CREW OXYGEN SYSTEM INSTALLATION OF ADDITIONAL CREW CYLINDER HAS BEEN EMBODIED | 200 | LOG | CAB | AV | 35 | 0.01 | 0.01 | COMP
VTL0273 | 777-52-195-00-01 | AFT CGO LIFT ACTUATOR FOUND NOISE DURING CLOSE | 800 | NRR | LWR | AI | 5200 | 0.01 | 8.51 | WIP
VTL0281 |  | AS PER B-KQX IPAD TECH LOG OPEN TL ENTRIES TL3733 - MCP APP ARM SWITCH LIGHT KEEPS FLICKERING AFTER ARMING APPROACH. | 200 | LOG | CAB | AV | 24 | 0.01 | 5.21 | WIP
VTL0299 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC003: CHIP IN CAPTAIN"S L1 WINDOW APPROXIMATELT 20CM IN FROM LEFT AND 15CM UP FROM BUTTOM. DOES NOT AFFECT VISION REF AMN 56-11-00/801 REV SEP18. | 200 | LOG | CAB | AI | 56 | 0.01 | 0.01 | COMP
VTL0307 | 777-C252500-01-07-01 | CABIN B ZONE LH PEY/EY CLASS DIVIDER 2EA MAGAZINE POCKET HOLD OPEN STRIP FOUND BROKEN | 200 | NRR | CAB | AI | 2500 | 3 | 3 | COMP
VTL0315 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC004: THIS AIRCARFT IS FITTEED WITH ETECHLOG AS THE MASTER MAINTENANCE RECORD. THE IPAD EFB DEVICE IS STORED IN THE AML/CDML.THE PAPER AML/CDML WILL REMAIN ONBOARD AS A BACKUP ONLY.COMPLY 365 IS INSTALLED IN BOTH FLICHT DECK IPAD AND CABIN IPAD WITH OPERATIONAL MANUALS | 200 | LOG | CAB | AI | 25 | 0.2 | 0.2 | COMP
VTL0323 |  | AS PER B-KQX DEFERRAL REPORT ITEM PADD P035: ETOPS (EDTO) VERIFICATION FLIGHT REQUIRED - REF AEO-29704, BOTH ENG EEC FADEC SOFTWARE UPGRADED EDTO VERIFICATION FLIGHT REQUIRED.(PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AV | 73 | 0.02 | 0.03 | DEFER
VTL0331 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC006: AEO-27365 INCORPORATED THE GOGO 2KU CONNECTIVITY RADOME STC. HKCAD STC-2018-11(FAA STC ST04240CH) ON THIS AIRCRAFT | 200 | LOG | CAB | AV | 44 | 0.01 | 0.01 | COMP
VTL0349 |  | AS PER B-KQX DEFERRAL REPORT ITEM PADD P034: EDTO VERIFICATION FLIGHT - PERFORM EDTO VERIFICATION FLIGHT DUE TO FUEL AND OIL SYSTEM DISTURBED ON BOTH ENGINES.(PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AE | 73 | 0.01 | 0.21 | OPEN
VTL0356 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC007: AEO-27365 INCORPORATED THE GOGO 2KU CONNECTIVITY RADOME STC. HKCAD STC-2018-12(FAA STC ST04241CH) ON THIS AIRCRAFT | 200 | LOG | CAB | AV | 44 | 0.01 | 0.01 | COMP
VTL0364 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC008:ACTIVE NTC/NTCC ENTRIES HAVE BEEN MIGRATED FROM PAPER TO E-TECHLOG WHICH IS NOW THE PRIMARY MEANS TO SCONSULT NTC/NTCC ON THIS AIRCRAFT TAIL. PAPER COPIES IN AML/CDML SHALL BE USED DURING PAPER FALLBACK ONLY.(REF:AEO-28695) | 200 | LOG | CAB | AI | 25 | 0.2 | 0.2 | COMP
VTL0372 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC009:"SB 777-22A0046/AEO-29595 AFCS S/W 2275-COL-AA6-12 EMNODIED ON THIS AIRCRAFT. THIS SB CANCELS FCOM OMB CAT-136 ERRONOUS AFDS GUIDANCE WHEN ILS SIGNAL INTERFERENCE OCCURS.THIS NTC IS VAILD UNTIL 1 MONTH AFTER ALL AIRCRAFT ARE EMBODIED" | 200 | LOG | CAB | AV | 22 | 0.2 | 0.2 | COMP
VTL0380 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC0010:AEO-29174/SB 777-31A0342 EMBODIED ON THIS AIRCRAFT, REFER TO FON " AIMS-2 BLOCK POINT V17C INTRODUCTION". THIS NTC IS VALID UNTIL FLEET UPGRADE COMPLETE" | 200 | LOG | CAB | AV | 31 | 0.01 | 0.01 | COMP
VTL0398 |  | AS PER B-KQX DEFERRAL REPORT ITEM ADD A105: MAINTENANCE INFORMATION ENTRY - AS WO/TASK:8280224/1 REQ'D, MLG SHOCK STRUTS SERVICING PERFORMED, PLS CHECK BOTH MLG SHOCK STRUT PRESSURE AFT 5-10 IN-SERVICE LANDING AND INFLATE AS NECESSARY. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 700 | LOG | LDG | AE | 32 | 0.01 | 0.21 | OPEN
VTL0406 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO FLIGHT AND GROUND CREW NTC0011:THE AIRCRAFT/ENGINES HAVE BEEN EQUIPPED WITH NEW FADEC SOFTWARE P/N 730A-GEC-A08-06 (A.0.8.6) REF SB 777-73-0037/AEO-29704. | 400 | LOG | ENG | AV | 73 | 0.2 | 0.2 | COMP
VTL0414 |  | AS PER B-KQX DEFERRAL REPORT ITEM ADD A110: LANDING GEAR, ALL - NO #11 MAIN WHEEL AND RH NOSE WHEEL INFLATION VALVE DUST CAPS MISSING. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 700 | LOG | LDG | AE | 32 | 0.01 | 0.21 | COMP
VTL0422 |  | AS PER B-KQX DEFERRAL REPORT ITEM ADD A111: FUSELAGE - EXTERNAL EXTRICAL PANEL NOT FLUSH WHEN CLOSED. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 100 | LOG | FUS | AE | 51 | 0.01 | 9.71 | WIP
VTL0430 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO CABIN AND GROUND CREW NTCC001:THIS AIRCRAFT IS FITTED WITH THE ETECHLOG AS THE MASTER MAINTENANCE PELOAD. THE IPAD EFB DEVICE IS STORED IN THE AML/CDML. THE PAPER AML/CDML WILL REMAIN ONBOARD AS A BACKUP ONLY. COMPLY IS INSTALLED IN BOTH FLIGHT DECK IPAD AND CABIN IPAD WITH OPERATIONAL MANUALS. | 200 | LOG | CAB | AI | 25 | 0.2 | 0.2 | COMP
VTL0448 |  | AS PER B-KQX IPAD TECH LOG NOTICE TO CABIN AND GROUND CREW NTCC002:ACTIVE NTC/NTCC ENTRIES HAVE BEEN MIGRATED FROM PAPER TO E-TECHLOG WHICH IS NOW THE PRIMARY MEANS TO CONSULT NTC/NTCC ON THIS AIRCRAFT TAIL.PAPER COPIES IN AML/CDML SHALL BE USED DURING PAPER FALLBACK ONLY.(REF:AEO-28695) | 200 | LOG | CAB | AI | 25 | 0.2 | 0.2 | COMP
VTL0455 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S091: APU - EDTO VERTIFICATION IN-FLIGHT START REQUIRED DUE APU REPLACED. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AE | 49 | 0.01 | 0.21 | COMP
VTL0463 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S092: POWERPLANT, ENGINE 1 - PLS DO A ONE TIME INSPECTION OF THE ENGINE 1 DMS SENSOR, LUBE UNIT SCAVENGE SCREENS AND MAGNETIC PLUGS BETWEEN 15 TO 20 CYCLES, TASK 79-00-00-200-804-H01 AND TASK 79-00-00-200-805-H01. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AE | 71 | 0.01 | 12.21 | OPEN
VTL0471 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S093: POWERPLANT, ENGINE 2 - PLS DO A ONE TIME INSPECTION OF THE ENGINE 2 DMS SENSOR, LUBE UNIT SCAVENGE SCREENS AND MAGNETIC PLUGS BETWEEN 15 TO 20 CYCLES, TASK 79-00-00-200-804-H01 AND TASK 79-00-00-200-805-H01.(PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AE | 71 | 0.01 | 12.21 | OPEN
VTL0489 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S094:PERFORM AEO-27666 PART 1,AND AEO-27669 PART 1 FOR THE CAPTAINS SEAT NO LATER THAN 6 FC AFTER OCTOBER 7,2022,UNTIL DECEMBER 31,2024.THE 6FC WILL BE FERRY FLIGHTS WITH NO PASSENGERS ON BOARD.AFTER EMBOIDIMENT OF MODIFICATIONS AS PER AEO-27666 PART 1,AND AEO-27669 CONTINUE TO SWS (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.22 | OPEN
VTL0497 | 777-52-190-00-01 | FWD CGO LIFT ACTUATOR FOUND NOISE DURING CLOSE | 800 | NRR | LWR | AI | 5200 | 0.01 | 8.51 | WIP
VTL0505 | 777-52-190-00-01 | FWD CGO DOOR FWD & AFT ROTARY ACTUATOR FOUND NOISE DURING CLOSE | 800 | NRR | LWR | AI | 5200 | 0.01 | 13.01 | OPEN
VTL0513 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S095: FIRST OFFICERS SEAT PERFORM AEO-27666 PART 2, AND AEO-27669 PART 2 FOR THE FIRST OFFICERS SEAT NO LATER THAN 6 FC AFTER OCTOBER 7,2022 UNTIL DECEMBER 31,2024.THE 6 FC WILL BE FERRY FLIGHTS WITH NO PASSENGERS ON BOARD.AFTER EMBOIDIMENT OF THE MODIFICATION CONTINUE TO SWS (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.22 | OPEN
VTL0521 | 777-57-814-01-01 | FOR MAINT REQ'D, DEACTIVE AND REACTIVE THE L/E SLATS SYS. | 500 | NRR | WNG | AE | 2700 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL0539 | 777-57-814-01-01 | FOR C-CHK OPS, L/E SLAT SYS MANUAL OPERATION REQ'D. | 500 | NRR | WNG | AE | 2781 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL0547 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S096: ACCOMPLISH AMS TASK 28-AWL-01 AND AMS TASK 28-AWL-03 WITHIN 5 FC OR 25 FH,WHICHEVER COMES FIRST AFTER STORAGE REACTIVATION FOR FERRY FLIGHT FROM ASP TO NEXT MRO FACILITY WHERE THE AIRCRAFT WILL BE PERFORMING BASE MAINT CHECK.UNTIL THEN ONLY NON PASSENGER CONTINUE TO SWS (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 500 | LOG | F/T | AV | 28 | 0.01 | 8.22 | WIP
VTL0554 | 777-57-856-01-01 | FOR MAINT REQ'D, DEACTIVE AND REACTIVE THE T/E FLAP SYS. | 500 | NRR | WNG | AE | 2700 | 0 | 0 | OPEN | For maintenance only, No charge to CX
VTL0562 | 777-C250008-01-01-01 | CAB - GALLEY 6 OVEN # 4(615) OPERATIONAL TEST FOUND NOISE SOUNDING. | 200 | NRP | CAB | AI | 2532 | 0.01 | 1.91 | WIP
VTL0570 | 777-53-904-00-01 | CABIN FB2 SEAT PARTITION SIDE CONSOLE AREA TEDLAR BUBBLE AT 18K 20G 23G 23KTOTAL 4 EA | 200 | NRR | CAB | SS | 2500 | 0.01 | 47.51 | WIP
VTL0588 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S098: ITEM NOT FOUND IN FAULT TREE (REFER TO REMARK) - AS PER CX WO TASK 9540228/1. FUNCTIONAL CHECK THE OVERHEAD FLIGHT CREW REST AND THE OVERHEAD FLIGHT ATTENDANT BACK UP LIGHTING POWER CAPACITY CHECK.(PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 2.21 | OPEN
VTL0596 | 777-53-904-00-01 | CAB #1 DOOR S1 STOWAGE FWD AND OFCR FWD B/HEAD TEDLAR FOUND SCRATCHED | 200 | NRR | CAB | SS | 2500 | 0.01 | 29.01 | WIP
VTL0604 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S099: ITEM NOT FOUND IN FAULT TREE (REFER TO REMARK) - AS PER CX WO 9540227/1 IFE SYSTEM WIRING INSPECTION. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 23 | 0.01 | 6.21 | COMP
VTL0612 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S100: ELECTRICAL POWER - DURING AIRCRAFT STORAGE IDGS WERE PRSERVED ON WING. REMOVE ENG #1 IDG FOR SHOP VISIT WITHIN MAXIMUM OF 25 FLIGHT HOURS FOR SHOP VISIT (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AE | 24 | 0.01 | 33.21 | WIP
VTL0620 | 777-53-908-00-01 | CABIN #2 DOOD G2 GLY L/R AISLE S/W ARED TADLAR FOUND SCRATCHED | 200 | NRR | CAB | SS | 25 | 0.01 | 29.01 | WIP
VTL0638 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S102: CENTRAL MAINT. COMPUTER (CMC) - REF WO:9539996/1 PN:G45002-2. SN:BCN3XZ1 REPLACE MAINTENANCE LAPTOP FOR SCHEDULE MAINTENANCE AT WORKSHOP. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 31 | 0.01 | 1.21 | OPEN
VTL0646 | 777-53-904-00-01 | CAB #1 DOOR SCL-01 & SCR-01 UPPER B/HEAD TEDLAR FOUND SCRATCHED | 200 | NRR | CAB | SS | 2500 | 0.01 | 0.01 | WIP
VTL0653 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S103: EQUIPMENT & FURNISHINGS - REF WO: 9539988/1 PN:62771-119. SN:0837 REPLACE L2 DOOR SLIDE RAFT ASSY: (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 3.91 | OPEN
VTL0661 | 777-53-920-00-01 | CAB-G8 GLY L/H AND R/H S8-01 COMPT DR TEDLAR FND DENT. | 200 | NRR | CAB | SS | 2500 | 0.01 | 15.51 | COMP
VTL0679 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S104: EQUIPMENT & FURNISHINGS - REF WO 9539986/1 PN: 63604-332. SN:0704 REPLACE R4 DOOR SLIDE RAFT ASSY (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 3.91 | OPEN
VTL0687 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S105: EQUIPMENT & FURNISHINGS - REF WO TASK 9539985/1 PN:5A3109-2. SN:ST0946 REPLACE RH OVERWING DOOR SLIDE ASSEMBLY (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 6.81 | WIP
VTL0695 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S106: EQUIPMENT & FURNISHINGS - REF WO 9539999/1 PN:BPAS10-5. SN:2813 L3 OVERWING DOOR REPLACE EPAS BATTERY (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 52 | 0.01 | 3.41 | WIP
VTL0703 | 777-53-904-00-01 | CABIN #1 DOOR OFCR DOOR AISLE S/W FOUND SCRATCHED | 200 | NRR | CAB | SS | 2500 | 0.01 | 15.01 | WIP
VTL0711 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S107: EQUIPMENT & FURNISHINGS - REF WO 9540004/1 PN:BPAS10-5. SN:2782 R3 OVERWING DOOR REPLACE EPAS BATTERY (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 52 | 0.01 | 3.41 | WIP
VTL0729 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S108: EQUIPMENT & FURNISHINGS - REF WO 9539997/1 PN:BPAS10-5. SN:2942 L3 OVERWING DOOR -REPLACE DOOR BACK UP BATTERY (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 52 | 0.01 | 3.41 | OPEN
VTL0737 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S109: EQUIPMENT & FURNISHINGS - REF WO 9539998/1 PN:BPAS10-5. SN: 2901 R3 OVERWING DOOR REPLACE BACKUP BATTERY (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 52 | 0.01 | 3.41 | WIP
VTL0745 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S110: EQUIPMENT & FURNISHINGS - REF WO 9540002/1 PN:41004509-1. SN: 61307A7 DOOT 4R REPLACE EPAS SQUIB (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.21 | OPEN
VTL0752 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S111: EQUIPMENT & FURNISHINGS - REF WO 954000/1 PN:41004509-1. SN:61095A7 DOOR 2R- REPLACE EPAS SQUIB (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.21 | OPEN
VTL0760 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S112: EQUIPMENT & FURNISHINGS - REF WO: 9540001/1 PN:41004509-1 SN:42111A7 DOOR 5 L REPLACE EPAS SQUIB (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.21 | OPEN
VTL0778 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S113: CREW INFORMATION SYSTEMS (EFB) - REF WO 9539995/1 CARRY OUT NETWORK FILE SERVER SECURITY LOGS DOWNLOAD (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 46 | 0.01 | 2.21 | OPEN
VTL0786 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S114: EQUIPMENT & FURNISHINGS - REF WO 9540003/1 PN:41004509-1. SN: 61089A7 DOOR 2L REPLACE EPAS SQUIB (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.21 | OPEN
VTL0794 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S115: ITEM NOT FOUND IN FAULT TREE (REFER TO REMARK), ENGINE 1 - ENG-1 WIRE SHIELD GND TERMINAL LUG MISSING AT CONNECTOR DM24001C (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 400 | LOG | ENG | AV | 71 | 0.01 | 0.21 | OPEN
VTL0802 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S116: ITEM NOT FOUND IN FAULT TREE (REFER TO REMARK) - AFT CARGO PDU 7R WIRING DAMAGED (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 4.21 | WIP
VTL0810 | 777-C252420-01-02-02 | CAB - SEAT 18G PCU TTL BUTTON O/P TEST FOUND NO RESP. | 200 | NRR | CAB | AV | 2502 | 2 | 2 | WIP
VTL0828 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S117:OXYGEN - QTY09 POTABLE OXY BOTTLES DUE FOR OVERHAUL AT FOLLOWING LOCATIONS. DR 2L,DR 2R,LH CTR DOG HOUSE FWD OF LAV E,RH CTR DOG HOUSE FWD OF LAV F,RH CTR DOG HOUSE FWD OF LAV F,LH CTR DOG HOUSE FWD OF GALLER 4,RH CTR DOG HOUSE FWD OF GALLEY 4,DR 5L STR STOWAGE CONTINUE TO SWS (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AV | 35 | 0.01 | 9.22 | OPEN
VTL0836 | 777-900003-01-1-01 | CAB - DOOR L5 EMERGENCY LIGHT POWER PACK(M33407) FOUND LOW CAPACITY | 200 | NRP | CAB | AV | 3351 | 1 | 1 | OPEN
VTL0844 | 777-C252500-01-07-01 | CABIN D ZONE G5 GLY AFTER LH MAGAZINE POCKET FOUND LOOSE | 200 | NRR | CAB | AI | 2500 | 1 | 1 | OPEN
VTL0851 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S118: LANDING GEAR, LEFT & RIGHT - LH AND RH MLG STEERING ACTUATORS RETURN LINES CHAFING ON GUIDE BRACKET.INNER BRAID EXPOSED. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 700 | LOG | LDG | AE | 32 | 0.01 | 0.21 | COMP
VTL0869 | 777-53-920-00-01 | CABIN D LAV FLR PAN RETAINER FOUND DETACH | 200 | NRR | CAB | AI | 2500 | 1 | 1 | OPEN
VTL0877 | 777-23-000-07-CX-R-01 | CAB - SEAT 41H SVDU O/P TEST FOUND NO RESP. | 200 | NRR | CAB | AV | 2332 | 2 | 2 | WIP
VTL0885 |  | AS PER B-KQX DEFERRAL REPORT ITEM SADD S119: PORTABLE FIRE EXTINGUISHERS (CABIN) - PORTABLE FIRE EXTINGUISHER LOCATED AT FLT ATT REST R/H EXPIRY DATE IS LESS THAN 4.5 MONTH. (PLEASE REFER TO ATTACHED “CX DEFERRAL REPORT” FOR THE REQUIRED ACTION ITEMS). | 200 | LOG | CAB | AI | 25 | 0.01 | 0.21 | COMP
VTL0893 | 777-53-870-00-01 | BULK CGO L/H AFT END WALL SURFACE FOUND DENT MARK | 100 | NRR | LWR | AI | 2500 | 4 | 4 | OPEN
VTL0901 | 777-53-920-00-01 | CABIN ALL LAV DOOR LOWER BUMPER FOUND MISSING | 200 | NRR | CAB | AI | 2500 | 3 | 3 | COMP
VTL0919 | 777-53-920-00-01 | CABIN E LAV CEILING AIR OUTLET FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL0927 | 777-53-920-00-01 | CABIN J LAV CEILING AIR OUTLET FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | WIP
VTL0935 | 777-53-920-00-01 | CABIN K LAV CEILING AIR OUTLET FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | WIP
VTL0943 | 777-53-920-00-01 | CABIN M LAV CEILING AIR OUTLET FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | WIP
VTL0950 | 777-53-920-00-01 | CABIN K LAV EXT DOOR UPPER METAL TRIM MISSING | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL0968 | 777-C330000-01-02-01 | CAB - DOOR L5 ATTENDANT CEILING WORK LIGHT LENS FOUND MISSING. | 200 | NRR | CAB | AV | 3322 | 1 | 1 | WIP
VTL0976 | 777-53-920-00-01 | CABIN L LAV FLR PAN RETAINER FOUND DETACH | 200 | NRR | CAB | AI | 2500 | 1 | 1 | WIP
VTL0984 | 777-53-920-00-01 | CABIN J LAV AISLE SIDE KICK STRIP FOUND DETACH | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL0992 | 777-53-920-00-01 | CABIN D LAV FWD DOGHOUSE INSIDE FOUND DENT | 200 | NRR | CAB | AI | 2500 | 3 | 3.6 | WIP | Cover page mhr is required
VTL1008 | 777-53-920-00-01 | CABIN G4R GLY UPPER FOAM SEAL DETACH | 200 | NRR | CAB | AI | 2500 | 1 | 1 | OPEN
VTL1016 | 777-C330000-01-03-01 | CAB - LAV CALL SWITCH LENS FOUND CRACKED AT LAV A, B K. | 200 | NRR | CAB | AV | 3325 | 2 | 2 | WIP
VTL1024 | 777-53-920-00-01 | CABIN G6 GLY OVEN COMPARTMENT LWR TRIM BROKEN | 200 | NRR | CAB | AI | 2500 | 3 | 3 | COMP
VTL1032 | 777-53-920-00-01 | CABIN G6/7 GLY FWD BULKHEAD "THE ATTENDANT SEAT MUST...." PLACARD DETACH | 200 | NRR | CAB | AI | 2500 | 2 | 2 | OPEN
VTL1040 | 777-53-920-00-01 | CABIN DOOR 5 S8 GLY S8-1 COMPT DR KICK STRIP DETACH | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL1057 | 777-53-920-00-01 | CABIN DOOR 5 S8 GLY S8-11 COMPT DR LWR METAL TRIM FOUND DEFORM | 200 | NRR | CAB | AI | 2500 | 0.01 | 5.51 | WIP
VTL1065 | 777-53-920-00-01 | CABIN STA1014 CEILING AREA 1EA AIR DUCT FOUND LOOSE | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL1073 | 777-C330000-01-02-01 | CAB - GALLEY AREA CEILING LIGHT FOUND LAMP OFF AT FWD GALLEY AND AFT GALLEY | 200 | NRR | CAB | AV | 3327 | 3 | 3 | WIP
VTL1081 | 777-C252000-01-02-01 | CABIN PAX ENTRY DOOR #1 AND C.D.E ZONE ALL AISLE AREA FLOOR CARPETS FOUND WORN. | 200 | NRP | CAB | SS | 2527 | 0.01 | 208.01 | WIP
VTL1099 | 777-C252000-01-02-01 | CABIN PAX ENTRY DOOR #1 AND C.D.E F ZONE ALL AISLE AREA REMOVED FLOOR CARPETS AREA FLOOR PNL SURFACE FOUND RESIDUAL DOUBLE TAPE . | 200 | NRP | CAB | CL | 2527 | 64 | 64 | COMP
VTL1107 | 777-C252000-01-02-01 | M/D UNDER SEAT FLOOR CARPETS FOUND WORN-STA1035 TO 1464. | 200 | NRP | CAB | SS | 2527 | 0.01 | 107.51 | WIP
VTL1115 | 777-53-904-00-01 | CAB FB2 SEAT RETRACTABLE ARM REST FND LOOSEN AT 12A 15A 16A 17A 18A19A 21A 23A | 200 | NRR | CAB | AI | 25 | 44 | 44 | OPEN
VTL1123 | 777-53-904-00-01 | CAB FB2 SEAT RETRACTABLE ARM REST FND LOOSEN AT 15D 16D 17D 18D 20D 21D 22D | 200 | NRR | CAB | AI | 25 | 38.5 | 38.5 | OPEN
VTL1131 | 777-53-904-00-01 | CAB FB2 SEAT RETRACTABLE ARM REST FND LOOSEN AT 11G 12G 15G 16G 17G 18G 20G 21G 22G 23G | 200 | NRR | CAB | AI | 25 | 55 | 55 | OPEN
VTL1149 | 777-53-904-00-01 | CAB FB2 SEAT RETRACTABLE ARM REST FND LOOSEN AT 11K 12K 15K 16K 17K 18K 19K 21K 22K 23K | 200 | NRR | CAB | AI | 25 | 55 | 55 | OPEN
VTL1156 | 777-53-904-00-01 | CAB FB2 SEAT TV MONITOR FND WEAK DURING OPENING AT 20D 21D 15G 20G 11K 16K 17K | 200 | NRR | CAB | AI | 25 | 0.01 | 23.51 | COMP
VTL1164 |  | AS PER CUSTOMER REQUEST, REMOVE DFDR (P/N 980-4750-009,S/N FDR02507) AND RETURN TO STORE | 200 | CUS | CAB | AV | 3131 | 0.01 | 4.51 | OPEN
VTL1172 | 777-53-904-00-01 | CAB FB2 SEAT MEAL TABLE FND LOOSEN AT 11A 15A 16A 17A | 200 | NRR | CAB | AI | 25 | 10 | 10 | COMP
VTL1180 | 777-53-904-00-01 | CAB FB2 SEAT MEAL TABLE FND LOOSEN AT 12D 15D 16D 17D 18D 23D | 200 | NRR | CAB | AI | 25 | 15 | 15 | COMP
VTL1198 | 777-53-904-00-01 | CAB FB2 SEAT MEAL TABLE FND LOOSEN AT 11G 15G 16G 17G 20G 21G 22G 23G | 200 | NRR | CAB | AI | 25 | 20 | 20 | COMP
VTL1206 | 777-53-904-00-01 | CAB FB2 SEAT MEAL TABLE FND LOOSEN AT 11K 15K 16K 18K 21K 22K 23K | 200 | NRR | CAB | AI | 25 | 17.5 | 17.5 | COMP
VTL1214 | 777-53-904-00-01 | CAB FB2 SEAT ENTER SIDE LITERATURE FND LOOSEN AT 15A 16A 18A 21A 22A | 200 | NRR | CAB | AI | 25 | 10 | 10 | WIP
VTL1222 | 777-53-904-00-01 | CAB FB2 SEAT ENTER SIDE LITERATURE FND LOOSEN AT 16D 17D 22D | 200 | NRR | CAB | AI | 25 | 6 | 6 | WIP
VTL1230 | 777-53-904-00-01 | CAB FB2 SEAT ENTER SIDE LITERATURE FND LOOSEN AT 11G 12G 15G 16G 17G 20G | 200 | NRR | CAB | AI | 25 | 12 | 12 | WIP
VTL1248 | 777-53-904-00-01 | CAB FB2 SEAT ENTER SIDE LITERATURE FND LOOSEN AT 11K 12K 16K 18K | 200 | NRR | CAB | AI | 25 | 8 | 8 | WIP
VTL1255 | 777-53-904-00-01 | CAB FB2 SEAT 17K RH SIDE STOWAGE TRIM FND LOOSEN | 200 | NRR | CAB | AI | 25 | 1 | 1 | OPEN
VTL1263 | 777-53-904-00-01 | CAB FB2 SEAT 11G LH SIDE STOWAGE TRIM FND LOOSEN | 200 | NRR | CAB | AI | 25 | 2 | 2 | OPEN
VTL1271 | 777-53-904-00-01 | CAB S2CL-11 COMPT DR TRIM FND STIFF | 200 | NRR | CAB | AI | 25 | 2 | 2 | COMP
VTL1289 | 777-53-904-00-01 | CAB S2CL-11 PLACARD FND BROKEN PN F0424391 | 200 | NRR | CAB | AI | 25 | 1 | 1 | COMP
VTL1297 | 777-53-904-00-01 | CAB FB2 SEAT 15G LH SIDE ARM REST PAD FND CRACK | 200 | NRR | CAB | AI | 25 | 2 | 2 | COMP
VTL1305 | 777-53-904-00-01 | CAB LAV D WATER FAUCET WATER FLOW TIME NOT ENOUGH | 200 | NRR | CAB | AI | 25 | 2 | 2 | OPEN
VTL1313 | 777-53-904-00-01 | CAB LAV E WATER FAUCET WATER FLOW TIME NOT ENOUGH | 200 | NRR | CAB | AI | 25 | 2 | 2 | OPEN
VTL1321 | 777-53-904-00-01 | CAB LAV F WATER FAUCET WATER FLOW TIME NOT ENOUGH | 200 | NRR | CAB | AI | 25 | 2 | 2 | OPEN
VTL1339 | 777-900003-01-1-01 | FOUND FWD CARGO LOADING LIGHT (DOOR-MOUNTED) LOWER 2 EA NOT ILLUMINATED. | 100 | NRP | LWR | AV | 3331 | 2 | 2 | COMP
VTL1347 | 777-900003-01-1-01 | FOUND AFT CARGO LOADING LIGHT (DOOR-MOUNTED) LOWER 2 EA NOT ILLUMINATED. | 100 | NRP | LWR | AV | 3331 | 2 | 2 | COMP
VTL1354 | 777-53-920-00-01 | CABIN D ZONE LHS NO.7,11,17 PAX WINDOW REVEAL DUST COVER FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 6 | 6 | COMP
VTL1362 | 777-53-920-00-01 | CABIN C ZONE RH SEAT ROW 54HJK PAX WINDOW REVEAL DUST COVER FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL1370 | 777-C252500-01-05-01 | CABIN B ZONE LHS NO.2 PAX WINDOW REVEAL FOUND DIRTY | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL1388 | 777-53-854-00-01 | AFT CGO R3 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1396 | 777-53-854-00-01 | AFT CGO R4 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1404 | 777-53-854-00-01 | AFT CGO R5 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1412 | 777-53-854-00-01 | AFT CGO R6 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1420 | 777-53-854-00-01 | AFT CGO R7 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1438 | 777-53-854-00-01 | AFT CGO R8 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1446 | 777-53-854-00-01 | AFT CGO L5 SIDE WALL PNL FOUND TORN | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL1453 | 777-53-870-00-01 | BULK CGO DOOR ENTRY AREA FLR PNL SURFACE 4EA PLACARD FOUND TORN | 100 | NRR | LWR | AI | 2500 | 4 | 4 | OPEN
VTL1461 | 777-53-870-00-01 | BULK CGO 2EA DOOR NET FOUND TORN | 100 | NRR | LWR | SS | 2500 | 0.1 | 0.1 | OPEN
VTL1479 | 777-C252500-01-05-01 | CABIN B ZONE LHS NO.7,8,9,10,13 PAX WINDOW REVEAL DUST COVER FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 10 | 10 | COMP
VTL1487 | 777-C252500-01-05-01 | CABIN B ZONE RHS NO.12 PAX WINDOW REVEAL DUST COVER FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL1495 | 777-53-515-00-01 | FWD CGO DOOR CUTOUT LWR SILL #4 ROLL OUT LATCH SPRING FOUND BROKEN | 100 | NRR | LWR | AI | 2500 | 0.1 | 0.1 | COMP
VTL1503 | 777-C252500-01-05-01 | CABIN A ZONE LHS NO.12 PAX WINDOW REVEAL FOUND DIRTY | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL1511 | 777-C252500-01-05-01 | CABIN A ZONE RHS NO.6 PAX WINDOW REVEAL DUST COVER FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL1529 | 777-900001-01-1-01 | R/H AFT LOGO LIGHT INOP | 300 | NRP | EMP | AV | 3345 | 0.01 | 6.51 | WIP
VTL1537 | AEO-27641-01 | DISCONNECT AND RECONNECT MAIN BATTERY AND APU BATTERY FOR MAINTENANCE | 100 | NRM | LWR | AV | 2420 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1545 | 777-53-534-00-01 | REMOVE LOWER AFT VHF ANTENNA FOR INSPECTION | 100 | NRR | FUS | AV | 2312 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1552 | 777-53-920-00-01 | CABIN C ZONE SEAT ROW 49D,54D,54G,&57 A O/H BIN EDGE TRIM FOUND DETACH | 200 | NRR | CAB | AI | 2500 | 6 | 6 | COMP
VTL1560 | 777-C254000-01-02-01A | CABIN E LAV TOILET SHROUD SEAT PAN FOUND CRACK | 200 | NRR | CAB | AI | 2540 | 2 | 2 | COMP
VTL1578 | 777-C254000-01-02-01A | CABIN B,L,J LAV TOILET SHROUD DAMPER STRIKE PLATE FOUND MISSING | 200 | NRR | CAB | AI | 2540 | 3 | 3 | COMP
VTL1586 | 777-900003-01-1-01 | FOUND FWD CARGO INTERIOR CEILING LIGHT L33828, L33818 NOT ILLUMINATED. | 100 | NRP | LWR | AV | 3337 | 2 | 2 | OPEN
VTL1594 | 777-900003-01-1-01 | FOUND NLG W/W SERVICE LIGHT NOT ILLUMINATED. | 100 | NRP | LWR | AV | 3331 | 1 | 1 | OPEN
VTL1602 | 777-C252000-01-02-01 | COCKPIT ALL CARPETS FOUND WORN | 200 | NRP | CAB | CL | 2527 | 0.01 | 24.01 | WIP
VTL1610 | 777-53-832-00-01 | PLS DISCONNECT THE LOWER BODY ANTI-COLLISION LIGHT CONNECTIONS FOR ACC | 100 | NRR | FUS | AV | 53 | 0.01 | 2.51 | WIP
VTL1628 | 777-900003-01-1-01 | MAINT MSG:32-54357 TIRE PRESSURE SENSOR (09) HAS LOSS OF REDUNDANT DATA. | 100 | NRP | LWR | AV | 3249 | 0.01 | 7.01 | OPEN
VTL1636 | 777-32-330-00-01 | NOSE LANDING GEAR W/W AREA FND DIRTY | 700 | NRR | LDG | CL | 32 | 10 | 10 | COMP
VTL1644 | 777-32-310-00-02 | RH MLG W/W AREA FND DIRTY | 700 | NRR | LDG | CL | 32 | 24 | 24 | COMP
VTL1651 | 777-32-320-00-01 | LH MLG W/W AREA FND DIRTY | 700 | NRR | LDG | CL | 32 | 24 | 24 | COMP
VTL1669 | 777-32-310-00-02 | PLS APPLY RH MLG W/W CLEAN AREA | 700 | NRR | LDG | AE | 32 | 8 | 8 | OPEN
VTL1677 | 777-C252500-01-04-01 | CABIN R1 DOOR AFTER CLOSET S1R-22 COMPARTMENT SLIDING SHELF FOUND LOOSEN | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL1685 | 777-32-310-00-01 | PLS APPLY LH MLG W/W CLEAN AREA | 700 | NRR | LDG | AE | 32 | 8 | 8 | OPEN
VTL1693 | 777-32-330-00-01 | PLS APPLY CIC TO NOSE LANDING GEAR W/W CLEAN AREA | 700 | NRR | LDG | AE | 32 | 12 | 12 | COMP
VTL1701 | 777-900003-01-1-01 | MAINT MSG:32-54369 TIRE PRESSURE SENSOR (12) HAS LOSS OF REDUNDANT DATA. | 100 | NRP | LWR | AV | 3249 | 0.01 | 7.01 | OPEN
VTL1719 | 777-900001-01-1-01 | NO.1 ENG INLET COWL LIP FOUND MINOR SURFACE CORROSION | 400 | NRP | ENG | SM | 7100 | 0.01 | 79.01 | WIP
VTL1727 | 777-900001-01-1-01 | NO.2 ENG INLET COWL LIP FOUND MINOR SURFACE CORROSION | 400 | NRP | ENG | SM | 7100 | 0.01 | 168.01 | WIP
VTL1735 | 777-900001-01-1-01 | NO.1 ENG INLET COWL INNER BARREL FOUND PAINT CHIPPED. | 400 | NRP | ENG | PT | 7100 | 12 | 12 | OPEN
VTL1743 | 777-900001-01-1-01 | NO.2 ENG INLET COWL INNER BARREL FOUND PAINT CHIPPED. | 400 | NRP | ENG | PT | 7100 | 12 | 12 | OPEN
VTL1750 | 777-900001-01-1-01 | NO.2 ENG BOTH SIDE FAN COWL INNER SURFACE FOUND PAINT CHIPPED | 400 | NRP | ENG | PT | 7100 | 12 | 12 | OPEN
VTL1768 | 777-71-842-01-01 | NO.1 ENG BOTH SIDE T/R COWL INNER BARREL REAR AREA FOUND PAINT CHIPPED | 400 | NRR | ENG | PT | 7800 | 16 | 16 | OPEN
VTL1776 | 777-71-856-02-01 | NO.2 ENG BOTH SIDE T/R COWL INNER BARREL REAR AREA FOUND PAINT CHIPPED | 400 | NRR | ENG | PT | 7800 | 16 | 16 | OPEN
VTL1784 | 777-53-904-00-01 | CAB FB2 SEAT 11K RH UNDER PAX WINDOW LINER PAD FND LOOSEN | 200 | NRR | CAB | AI | 25 | 1 | 1 | COMP
VTL1792 | 777-C252500-01-04-01 | CABIN DOOR 1 GLY SEVERAL TURN BUTTON FOUND STIFF | 200 | NRR | CAB | AI | 2500 | 2 | 2 | OPEN
VTL1800 | 777-C252500-01-04-01 | CABIN DOOR 2 GLY SEVERAL TURN BUTTON FOUND STIFF | 200 | NRR | CAB | AI | 2500 | 2 | 2 | OPEN
VTL1818 | 777-C252500-01-04-01 | CABIN DOOR 4 GLY SEVERAL TURN BUTTON FOUND STIFF | 200 | NRR | CAB | AI | 2500 | 2 | 2 | OPEN
VTL1826 | 777-C252500-01-04-01 | CABIN DOOR 4 GLY SEVERAL TURN BUTTON FOUND STIFF | 200 | NRR | CAB | AI | 2500 | 2 | 2 | OPEN
VTL1834 | 777-C252500-01-04-01 | CABIN DOOR 5 GLY SEVERAL TURN BUTTON FOUND STIFF | 200 | NRR | CAB | AI | 2500 | 2 | 2 | COMP
VTL1842 | 777-900001-01-1-01 | NO.2 ENG INLET COWL LIP 3:00, 9:00 AREA FOUND SEALANT TORN. | 400 | NRP | ENG | AE | 7100 | 2 | 2 | OPEN
VTL1859 | 777-900001-01-1-01 | NO.1 ENG INLET COWL LIP 3:00, 9:00 AREA FOUND SEALANT TORN. | 400 | NRP | ENG | AE | 7100 | 2 | 2 | OPEN
VTL1867 | 777-C252500-01-04-01 | CABIN DOOR 1 CTR S1 STOWAGE COMPARTMENT DOOR LATCH FOUND STIFF | 200 | NRR | CAB | AI | 2500 | 1 | 1 | OPEN
VTL1875 | 777-C254000-01-08-01 | CABIN A LAV FLOOR PAN RETAINER FOUND DETACH | 200 | NRR | CAB | AI | 2540 | 1 | 1 | WIP
VTL1883 | 777-C254000-01-08-01 | CABIN B LAV TOILET SHROUD SUPPORT LOWER PANEL FOUND DETACH | 200 | NRR | CAB | AI | 2540 | 1 | 1 | COMP
VTL1891 | 777-C254000-01-08-01 | CABIN A LAV TOILET SHROUD SUPPORT PANEL FOUND CRACK | 200 | NRR | CAB | AI | 2540 | 3 | 3 | COMP
VTL1909 | 777-C254000-01-08-01 | CABIN A & B LAV CEILING AIR OUTLET FOUND CRACK | 200 | NRR | CAB | AI | 2540 | 2 | 2 | COMP
VTL1917 | 777-C252500-01-04-01 | CABIN B ZONE CTR S2C STOWAGE COUNTER TOP SEVERAL BUTTON FOUND DEFORM | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL1925 | 777-53-514-00-01 | REMOVE AND INSTALL CENTER RA RECEIVER AND TRANSMIT ANTENNA FOR INSPECTION | 100 | NRR | FUS | AV | 3433 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1933 | 777-53-514-00-01 | REMOVE AND INSTALL MARKER BEACON ANTENNA | 100 | NRR | FUS | AV | 3432 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1941 | 777-53-514-00-01 | REMOVE AND INSTALL DME ANTENNA FOR INSPECTION | 100 | NRR | FUS | AV | 3455 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1958 | 777-53-514-00-01 | REMOVE AND INSTALL ATC ANTENNA FOR INSPECTION | 100 | NRR | FUS | AV | 3453 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1966 | 777-53-514-00-01 | REMOVE AND INSTALL LOWER TCAS ANTENNA FOR INSPECTION | 100 | NRR | FUS | AV | 3445 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL1974 | 777-C254000-01-08-01 | CABIN F LAV TOILET SHROUD SUPPORT PANEL FOUND CRACK | 200 | NRR | CAB | AI | 2540 | 3 | 3.6 | WIP | Cover page mhr is required
VTL1982 | 777-C254000-01-08-01 | CABIN D LAV TOILET SHROUD SUPPORT PANEL FOUND CRACK | 200 | NRR | CAB | AI | 2540 | 3 | 3.6 | WIP | Cover page mhr is required
VTL1990 | 777-25-115-01-CX-01 | CAB BABY FLOTATION COT FND EXPIRY IN OVERHEAD BIN ABOVE SEAT 70ABC 1EA AND 70HJK 2EA PN A346600A00 | 200 | NRP | CAB | AI | 25 | 1 | 1 | OPEN
VTL2006 | 777-38-000-01-CX-01 | LAV SERVICE PNL 2EA LATCH FOUND SEAL MISSING | 100 | NRP | LWR | SM | 3800 | 0.01 | 6.51 | WIP
VTL2014 | 777-53-920-00-01 | CABIN #2 DOOR L/H PARTITION FWD UPPER TEDLAR FOUND DENT MARKS | 200 | NRR | CAB | SS | 25 | 4 | 4 | WIP
VTL2022 | 777-53-854-00-01 | AFT CGO EXTERIOR HANDLING CTL PNL LATCH SEAL FOUND MISSING | 100 | NRR | LWR | SM | 5200 | 0.01 | 6.51 | WIP
VTL2030 | 777-C330000-01-01-01 | CAB - SEAT 45AC SIDEWALL LIGHT FIXTURE FOUND NO RESP. | 200 | NRR | CAB | AV | 3321 | 2 | 2 | WIP
VTL2048 | 777-53-818-00-01 | FWD CGO STA697 R/H SIDE WALL POST UPR AREA 1EA ANCHOR NUT FOUND DAMAGED | 100 | NRR | LWR | SM | 2500 | 0.01 | 3.01 | WIP
VTL2055 | 777-53-818-00-01 | FWD CGO STA592 CEILING PNL RETAINER FOUND DEFORM | 100 | NRR | LWR | SM | 2500 | 0.1 | 0.1 | WIP
VTL2063 | 777-55-000-06-CX-01 | HF ANTENNA L/E NO.4 PANEL FE-AS COATING RESISTANCE CHECK OUT OF LIMIT | 300 | NRR | EMP | SS | 5124 | 0.01 | 53.03 | WIP | will changed to 49mhr
VTL2071 | 777-53-818-00-01 | FWD CGO STA592 RBL60 CEILING AREA 1EA STAND OFF FOUND BROKEN | 100 | NRR | LWR | SM | 2500 | 0.01 | 3.01 | WIP
VTL2089 | 777-53-818-00-01 | FWD CGO EXTERIOR HANDLING CTL PNL FOUND CORROSION | 100 | NRR | LWR | SM | 2500 | 0.51 | 7.52 | WIP | Cover page mhr is required
VTL2097 | 777-53-818-00-01 | FWD CGO EXTERIOR HANDLING CTL PNL 2EA LATCH FOUND CORROSION | 100 | NRR | LWR | SM | 2500 | 0.01 | 6.01 | WIP
VTL2105 | 777-53-818-00-01 | FWD CGO DOOR EXTERIOR CTL PNL HINGE SPRING FOUND BROKEN | 100 | NRR | LWR | SM | 2500 | 0.01 | 7.51 | WIP
VTL2113 | 777-900001-01-1-01 | CAB - PORTABLE OXY CYLINDER PRESSURE (1600PSI) LESS THAN 1800PSI INSIDE LH CTR DOGHOUSE FWD OF GALLEY 4. | 200 | NRP | CAB | AV | 3531 | 1 | 1 | OPEN
VTL2121 | 777-57-906-02-01 | FOUND DIRTY, PLS PERFORM THE CLEANING OF L/E CAVITY OF LHW AND RHW. | 500 | NRR | WNG | CL | 5700 | 32 | 32 | WIP
VTL2139 | 777-57-948-02-01 | FOUND DIRTY, PLS PERFORM THE CLEANING OF T/E CAVITY OF LHW AND RHW. | 600 | NRR | WNG | CL | 5700 | 40 | 40 | COMP
VTL2147 | 777-57-974-02-01 | FOUND DIRTY, PLS PERFORM THE CLEANING OF ALL THE FLAP SUPPORT FAIRINGS. | 600 | NRR | WNG | CL | 5700 | 18 | 18 | COMP
VTL2154 | 777-57-974-02-01 | FOUND FLAP TRACKS DIRTY, ALL FLAP TRACKS NEED CLEANING. | 600 | NRR | WNG | CL | 5700 | 18 | 18 | COMP
VTL2162 | 777 BASIC OPEN 600 | FOUND DIRTY AT WING RELATED PANELS, NEED CLEANING. | 600 | NRR | WNG | CL | 2700 | 10 | 10 | COMP
VTL2170 | 777-25-110-02-CX-01 | CAB DR 1 DR 2 DR 3 ATTENDANT SEAT LIFE JACKET FND EXPIRED TTL 8EA PN 0002508 | 200 | NRR | CAB | AI | 25 | 1 | 1 | COMP
VTL2188 | 777-57-521-00-01 | PLS PERFORM THE CLEANING AT LHW I/B FLAP TORQUE TUBE AND NEARBY AREA FOR INSP. | 500 | NRR | WNG | CL | 2751 | 6 | 6 | COMP
VTL2196 | 777-57-521-00-02 | PLS PERFORM THE CLEANING AT RHW I/B FLAP TORQUE TUBE AND NEARBY AREA FOR INSP. | 600 | NRR | WNG | CL | 2751 | 6 | 6 | COMP
VTL2204 | 777-25-110-02-CX-01 | CAB DR L4 1EA DR L5 2EA DR R5 AFT I/B 1EA ATTENDANT SEAT LIFE JACKET FND MISSING TTL 4EA PN 0002508 | 200 | NRR | CAB | AI | 25 | 1 | 1 | COMP
VTL2212 | 777-53-904-00-01 | CAB FB2 SEAT BACK PARTITION BLACK LINER AND FWD SIDE LINER FND DETACH FROM 11A TO 23A | 200 | NRR | CAB | AI | 25 | 6 | 6 | OPEN
VTL2220 | 777-53-904-00-01 | CAB FB2 SEAT BACK PARTITION BLACK LINER AND FWD SIDE LINER FND DETACH FROM 11D TO 23D | 200 | NRR | CAB | AI | 25 | 6 | 6 | OPEN
VTL2238 | 777-53-904-00-01 | CAB FB2 SEAT BACK PARTITION BLACK LINER AND FWD SIDE LINER FND DETACH FROM 11G TO 23G | 200 | NRR | CAB | AI | 25 | 6 | 6 | OPEN
VTL2246 | 777-53-904-00-01 | CAB FB2 SEAT BACK PARTITION BLACK LINER AND FWD SIDE LINER FND DETACH FROM 11K TO 23K | 200 | NRR | CAB | AI | 25 | 6 | 6 | OPEN
VTL2253 | 777-53-904-00-01 | CAB FB2 SEAT SIDE STOWAGE AREA RED CLOTH FND DETACH AT 16A 18A 9A | 200 | NRR | CAB | SS | 25 | 0.01 | 0.01 | OPEN
VTL2261 | 777-53-904-00-01 | CAB FB2 SEAT SIDE STOWAGE AREA RED CLOTH FND DETACH AT 12D 23D | 200 | NRR | CAB | SS | 25 | 0.01 | 0.01 | OPEN
VTL2279 | 777-32-330-00-01 | NOSE LANDING GEAR LH SPIN BRAKE INNER SUPPORT BRACKET FND CRACKED | 700 | NRR | LDG | AE | 32 | 4 | 4 | COMP
VTL2287 | 777-53-904-00-01 | CAB FB2 SEAT SIDE STOWAGE AREA RED CLOTH FND DETACH AT 11G 18G 21G | 200 | NRR | CAB | SS | 25 | 0.01 | 0.01 | OPEN
VTL2295 | 777-53-904-00-01 | CAB FB2 SEAT SIDE STOWAGE AREA RED CLOTH FND DETACH AT 16K 21K 23K | 200 | NRR | CAB | SS | 25 | 0.01 | 0.01 | OPEN
VTL2303 | 777-53-904-00-01 | CAB FB2 SEAT FOOT REST AREA AND SEAT SIDE BLACK LINER FND DIRTY FROM 11A TO 23A | 200 | NRR | CAB | CL | 25 | 6 | 6 | OPEN
VTL2311 | 777-53-904-00-01 | CAB FB2 SEAT FOOT REST AREA AND SEAT SIDE BLACK LINER FND DIRTY FROM 11D TO 23D | 200 | NRR | CAB | CL | 25 | 6 | 6 | OPEN
VTL2329 | 777-53-904-00-01 | CAB FB2 SEAT FOOT REST AREA AND SEAT SIDE BLACK LINER FND DIRTY FROM 11G TO 23G | 200 | NRR | CAB | CL | 25 | 6 | 6 | OPEN
VTL2337 | 777-53-904-00-01 | CAB FB2 SEAT FOOT REST AREA AND SEAT SIDE BLACK LINER FND DIRTY FROM 11K TO 23K | 200 | NRR | CAB | CL | 25 | 6 | 6 | OPEN
VTL2345 | 777-32-320-00-01 | LH NLG AFT DOOR UPPER AFT BONDING JUMPER AGED | 700 | NRR | LDG | AE | 32 | 0.01 | 3.51 | COMP
VTL2352 | 777-32-320-00-01 | RH NLG AFT DOOR UPPER AFT BONDING JUMPER AGED | 700 | NRR | LDG | AE | 32 | 0.01 | 3.51 | COMP
VTL2360 | 777-32-806-01-01 | LH MLG #10 WHEEL ASSY FND DEEP CUT | 700 | NRR | LDG | AE | 32 | 0.01 | 7.21 | WIP
VTL2378 | SWC-28028-01-01 | LH INLET DOOR ACT ACC DOOR 191LL O/B HINGLE WORN | 100 | NRW | FUS | AE | 32 | 0.01 | 3.01 | COMP
VTL2386 | 777-35-160-01-CX-01 | CAB - PORTABLE OXY MASK EXPIRY DATE FOUND LESS THAN 4.5 MONTHS AT DOOR 1L, DOOR 1R, RH CTR FWD OF LAV F, LH CTR FWD OF OFAR. | 200 | NRP | CAB | AV | 3531 | 1 | 1 | WIP
VTL2394 | 777-53-818-00-01 | ACCESS-REMOVE FWD CGO DOOR WAY CEILING AREA CGO DOOR CTL SWITCH AND HANDLING CTL SWITCH FOR CEILING PNL REMOVAL | 100 | NRR | LWR | AV | 2500 | 0.01 | 4.01 | WIP
VTL2402 | 777-53-904-00-01 | CAB DR 1 ENTER AREA FLOOR MAT SEAL FND WORN | 200 | NRR | CAB | AI | 25 | 4 | 4 | OPEN
VTL2410 | 777-53-854-00-01 | ACCESS-REMOVE AFT CGO DOOR WAY CEILING AREA CGO DOOR CTL SWITCH AND HANDLING CTL SWITCH FOR CEILING PNL REMOVAL | 100 | NRR | LWR | AV | 2500 | 0.01 | 4.01 | WIP
VTL2428 | 777-53-904-00-01 | CAB DR 2 ENTER AREA FLOOR MAT SEAL FND WORN | 200 | NRR | CAB | AI | 25 | 4 | 4 | COMP
VTL2436 | 777-52-816-01-01 | M/D L1 DOOR CUTOUT AND DOOR FRAME CUTOUT 5EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 10 | 10 | COMP
VTL2444 | 777-53-904-00-01 | CAB DR 4 ENTER AREA FLOOR MAT SEAL FND WORN | 200 | NRR | CAB | AI | 25 | 4 | 4 | COMP
VTL2451 | 777-53-904-00-01 | CAB DR 5 ENTER AREA FLOOR MAT SEAL FND WORN | 200 | NRR | CAB | AI | 25 | 4 | 4 | COMP
VTL2469 | 777-52-834-02-01 | M/D R1 DOOR CUTOUT AND DOOR FRAME CUTOUT 6EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 12 | 12 | COMP
VTL2477 | 777-52-820-01-01 | M/D L2 DOOR CUTOUT AND DOOR FRAME CUTOUT 6EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 12 | 12 | COMP
VTL2485 | 777-52-824-01-01 | M/D L3 DOOR CUTOUT AND DOOR FRAME CUTOUT 5EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 10 | 10 | COMP
VTL2493 | 777-53-904-00-01 | CAB FWD DR L2 PARTITION TRIM FND LOOSEN | 200 | NRR | CAB | AI | 25 | 2 | 2 | COMP
VTL2501 | 777-52-844-02-01 | M/D R3 DOOR CUTOUT AND DOOR FRAME CUTOUT 17EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 34 | 34 | COMP
VTL2519 | 777-52-827-01-01 | M/D L4 DOOR CUTOUT AND DOOR FRAME CUTOUT 11EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 22 | 22 | COMP
VTL2527 | 777-53-874-00-01 | BULK CGO L/H AFT FLR PNL SURFACE FOUND GOUGE | 100 | NRR | LWR | SM | 5300 | 22 | 22.05 | WIP | Cover page mhr is required
VTL2535 | 777-52-849-02-01 | M/D R4 DOOR CUTOUT AND DOOR FRAME CUTOUT 14EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 28 | 28 | COMP
VTL2543 | 777-52-831-01-01 | M/D L5 DOOR CUTOUT AND DOOR FRAME CUTOUT 4EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 8 | 8 | COMP
VTL2550 | 777-52-853-02-01 | M/D R5 DOOR CUTOUT AND DOOR FRAME CUTOUT 5EA PLASTIC PNLS FND CRACKED | 200 | NRR | CAB | AI | 25 | 10 | 10 | COMP
VTL2568 | 777-900003-01-1-01 | FOUND AFT CARGO POWERED DRIVE UNIT (PDU) 4R INOPERATION. | 100 | NRP | LWR | AI | 2553 | 0.01 | 4.01 | WIP
VTL2576 | 777-900003-01-1-01 | FOUND AFT CARGO POWERED DRIVE UNIT (PDU) 7R INOPERATION. | 100 | NRP | LWR | AI | 2553 | 0.01 | 0.01 | OPEN
VTL2584 | 777-900003-01-1-01 | FOUND AFT CARGO POWERED DRIVE UNIT (PDU) 15R INOPERATION. | 100 | NRP | LWR | AI | 2553 | 0.01 | 4.01 | WIP
VTL2592 | 777-53-804-00-01 | FUS NOSE RADOME AROUND LH SIDE SEAL WORN | 100 | NRR | FUS | AE | 53 | 6 | 6 | COMP
VTL2600 | 777-53-804-00-01 | FUS NOSE RADOME AROUND RH SIDE SEAL WORN | 100 | NRR | FUS | AE | 53 | 6 | 6 | COMP
VTL2618 | 777-33-000-00-CX-01 | AT RHW WINGTIP, FOUND THE ANTI-COLLISION LIGHT LENS SEPARATED FROM THE HOUSING. | 600 | NRR | WNG | AE | 3344 | 0.01 | 0.01 | OPEN
VTL2626 | 777-53-904-00-01 | CAB OFCR STAIRS STEP ANTISLIP TAPE FOUND DETACH | 200 | NRR | CAB | AI | 25 | 2 | 2 | COMP
VTL2634 | 777-53-904-00-01 | COCKPIT LH CLOSET SAFETY BELT FND MALFUNCTION | 200 | NRR | CAB | AI | 25 | 1 | 1 | COMP
VTL2642 | 777-53-854-00-01 | AFT CGO STA1434-1455 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | OPEN
VTL2659 | 777-53-904-00-01 | CAB DR R1 S1-11 CLOSET EXTENSION SEAT BELT BAG FND BROKEN | 200 | NRR | CAB | AI | 25 | 1 | 1 | COMP
VTL2667 | 777-53-854-00-01 | AFT CGO STA1434-1455 L/H & R/H SIDE WALL INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | OPEN
VTL2675 | 777-53-854-00-01 | AFT CGO STA1434-1455 BILGE AREA INSULATION BLANKET FOUND DIRTY | 100 | NRR | LWR | AI | 2500 | 6 | 6 | OPEN
VTL2683 | 777-53-854-00-01 | AFT CGO STA1455-1643 BILGE AREA INSULATION BLANKET FOUND DIRTY | 100 | NRR | LWR | AI | 2500 | 5 | 5 | OPEN
VTL2691 | 777-53-854-00-01 | AFT CGO STA1455-1643 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 5 | 5 | WIP
VTL2709 | 777-53-854-00-01 | AFT CGO STA1643-1886 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 5 | 5 | WIP
VTL2717 | 777-53-870-00-01 | BULK CGO STA1886-2062 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 5 | 5 | WIP
VTL2725 | 777-C252000-01-07-R-02 | FB2 PAX SEAT MANUAL COVER FOUND LOOSEN AT:11A 16A 11D 12G 16G 16K 12K 21A 22A 23A 22D 23G 22G 20G TTL:14EA | 200 | NRR | CAB | SS | 25 | 10.5 | 10.5 | OPEN
VTL2733 | 777-53-818-00-01 | FWD CGO STA409-613 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | WIP
VTL2741 | 777-53-818-00-01 | FWD CGO STA613-804 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | WIP
VTL2758 | 777-C252000-01-07-R-02 | FB2 PAX SEAT BACKREST ATT LEGREST LINE SCREW FOUND LOOSEN AT:11A 12A 17G 17K TTL:4EA | 200 | NRR | CAB | SS | 25 | 1.5 | 1.5 | OPEN
VTL2766 | 777-C252000-01-07-R-02 | FB2 PAX SEAT MANUAL COVER FOUND CRACKED AT:12A 19A 21G TTL:3EA | 200 | NRR | CAB | SS | 2520 | 3 | 3 | COMP
VTL2774 | 777-C252000-01-07-R-02 | FB2 PAX SEAT BACKREST ATT LEGREST LINE SCREW FOUND BROKEN AT:16A | 200 | NRR | CAB | SS | 25 | 0.01 | 3.01 | OPEN
VTL2782 | TA28000101 | FOUND MANY GASKETS DEFORMED, AT LHW FUEL TANK ACCESS DOORS. | 500 | NRR | F/T | AE | 5705 | 0.01 | 0.01 | COMP
VTL2790 | TA28000101 | FOUND MANY GASKETS DEFORMED, AT RHW FUEL TANK ACCESS DOORS. | 600 | NRR | F/T | AE | 5705 | 0.01 | 0.01 | COMP
VTL2808 | TA28000101 | FOUND MANY GASKETS DEFORMED, AT RHW FUEL TANK ACCESS DOORS. | 600 | NRR | F/T | AE | 5705 | 0.01 | 0.01 | COMP
VTL2816 | 777-53-544-00-01 | OVER WING TO BODY FAIRING 194FR 19AR 193EL FND SCREWS 4EA SEIZED | 100 | NRR | FUS | GW | 53 | 4 | 4 | COMP
VTL2824 | TA28000101 | FOUND MANY GASKETS DEFORMED, AT RHW FUEL TANK ACCESS DOORS. | 600 | NRR | F/T | AE | 5705 | 0.01 | 0.01 | COMP
VTL2832 | 777-53-544-00-01 | RH OVER WING TO BODY FAIRING 194FR 19AR 194CR FND ANCHOR NUTS BROKEN 4EA SEIZED | 100 | NRR | FUS | SM | 53 | 0.01 | 3.01 | WIP
VTL2840 | TA28000101 | FOUND DIRTY, AT LH FUEL TANK ACCESS DOORS, NEED CLEANING. | 500 | NRR | F/T | AE | 2800 | 8 | 8 | COMP
VTL2857 | 777-55-824-00-01 | V/STAB TIP FAIRING FOUND SEAL TORN | 300 | NRR | EMP | AE | 5500 | 3 | 3 | COMP
VTL2865 | 777-C252000-01-07-R-02 | FB2 PAX SEAT SEAT PAN ATT BRACKET ATT PIN &CLIP FOUND MISSING AT:11D | 200 | NRR | CAB | SS | 25 | 1 | 1 | COMP
VTL2873 | TA28000101 | FOUND DIRTY, AT RH FUEL TANK ACCESS DOORS, NEED CLEANING. | 500 | NRR | F/T | AE | 2800 | 8 | 8 | COMP
VTL2881 | 777-C252000-01-07-R-02 | FB2 PAX SEAT AIRBAG BELT LEATHER FOUND TORN AT:17D 18G 23D.G TTL:4EA | 200 | NRR | CAB | SS | 25 | 6 | 6 | WIP
VTL2899 | 777-C252000-01-07-R-02 | FB2 PAX SEAT PAN ATT BRACKET PIN CLIP FOUND MISSING AT:16A 15G 21A 23G TTL:4EA | 200 | NRR | CAB | SS | 25 | 2 | 2 | COMP
VTL2907 | 777-55-804-00-01 | RUDDER ACC PNL 324GL FOUND 3EA ANCHOR NUT BROKEN | 300 | NRR | EMP | SM | 2700 | 0.01 | 3.01 | WIP
VTL2915 | TA28000101 | FOUND DIRTY, AT RH FUEL TANK ACCESS DOORS, NEED CLEANING. | 500 | NRR | F/T | AE | 2800 | 0.01 | 0.01 | COMP
VTL2923 | 777-53-892-00-01 | FUS LOWER FWD &AFT WING TO BODY FAIRING FND SCREWS BROKEN | 100 | NRR | FUS | AE | 53 | 3 | 3 | OPEN
VTL2931 | 777-C252000-01-07-R-02 | FB2 PAX SEAT BACKREST ATT SEAT PAN SCREW FOUND MISSING AT:12K 15A 21D TTL:3EA | 200 | NRR | CAB | SS | 25 | 2 | 2 | COMP
VTL2949 | 777-53-892-00-01 | FUS LOWER FWD &AFT WING TO BODY FAIRING FND SCREWS BROKEN | 100 | NRR | FUS | AE | 53 | 3 | 3 | OPEN
VTL2956 | 777-C252000-01-07-R-02 | FB2 PAX SEAT BACKREST ATT SCREW FOUND LOOSEN AT:15K 21A 22A 21D 23K TTL;5EA | 200 | NRR | CAB | SS | 25 | 2.5 | 2.5 | OPEN
VTL2964 | 777-C252000-01-07-R-02 | FB2 PAX SEAT HEADREST SLIDE FIXED PLATE FOUND BROKEN AT:12D | 200 | NRR | CAB | SS | 25 | 1 | 1 | COMP
VTL2972 | 777-C252000-01-07-R-02 | FB2 PAX SEAT VELCRO TAPE FOUND LOOSEN AT:11A-23A 11D-23D TTL20EA | 200 | NRR | CAB | SS | 25 | 8.5 | 8.5 | COMP
VTL2980 | 777 BASIC OPEN 500 | FOUND MANY SCREWS HEAD DAMAGE, NEEDED DRILL OFF, AT BOTH WING T/E PANEL: 652LB,652CB,561QB,561JB AND ETC, TOTAL | 600 | NRR | WNG | GW | 5700 | 22 | 22 | COMP
VTL2998 | 777-C252000-01-07-R-02 | FB2 PAX SEAT VELCRO TAPE FOUND LOOSEN AT:11G-23G 11K - 23K TTL:20EA | 200 | NRR | CAB | SS | 25 | 8.5 | 8.5 | COMP
VTL3004 | 777-25-040-03-CX-01-01 | FB2 PAX SEAT INFLATOR FOUND EXPIRY AT:11A 12A 15A 16A 17A 18A 19A 21A 22A 23A TTL:10EA | 200 | NRR | CAB | SS | 25 | 15 | 15 | WIP
VTL3012 | 777-25-040-03-CX-01-01 | FB2 PAX SEAT INFLATOR FOUND EXPIRY AT:11D 12D 15D 16D 17D 18D 20D 21D 22D 23D TTL:10EA | 200 | NRR | CAB | SS | 25 | 15 | 15 | WIP
VTL3020 | 777-25-040-03-CX-01-01 | FB2 PAX SEAT INFLATOR FOUND EXPIRY AT:11G 12G 15G 16G 17G 18G 20G 21G 22G 23G TTL:10EA | 200 | NRR | CAB | SS | 25 | 15 | 15 | WIP
VTL3038 | 777-25-040-03-CX-01-01 | FB2 PAX SEAT INFLATOR FOUND EXPIRY AT:11K 12K 15K 16K 17K 18K 19K 21K 22K 23K TTL:10EA | 200 | NRR | CAB | SS | 25 | 15 | 15 | WIP
VTL3046 | 777-55-864-02-01 | RIGHT ELEVATOR ACC PNL 345CB,34DB,345EXB,345GXB FOUND 50EA SCREW HEADS IN POOR CONDITION | 300 | NRR | EMP | AE | 2700 | 2 | 2 | OPEN
VTL3053 | 777-52-814-00-01 | BULK CGO DOOR EXTERIOR HANDLE 1EA STUD FOUND MISSING | 800 | NRR | LWR | AI | 5200 | 5 | 5 | WIP
VTL3061 | 777-53-920-00-01 | CABIN B ZONE SEAT ROW 30D&33G O/H BIN EDGE TRIM FOUND DETACH | 200 | NRR | CAB | AI | 2500 | 3 | 3 | COMP
VTL3079 | 777-55-804-00-01 | V/STAB ACC PNL 322FL, 322EL, 327,324CXL,324DXL,324HL FOUND 100EA SCREW HEADS IN POOR CONDITION | 300 | NRR | EMP | AE | 5500 | 2 | 2 | OPEN
VTL3087 | 777-C252500-01-08-01 | CABIN B ZONE L/R O/H BIN INTERNAL UPPER FRAME FOUND DENT | 200 | NRR | CAB | AI | 2500 | 10 | 10.6 | WIP | Cover page mhr is required
VTL3095 | 777-C252500-01-08-01 | CABIN C ZONE L/R O/H BIN INTERNAL UPPER FRAME FOUND DENT | 200 | NRR | CAB | AI | 2500 | 20 | 20.6 | WIP | Cover page mhr is required
VTL3103 | 777-C252500-01-08-01 | CABIN D ZONE L/R O/H BIN INTERNAL UPPER FRAME FOUND DENT | 200 | NRR | CAB | AI | 2500 | 20 | 20.6 | WIP | Cover page mhr is required
VTL3111 | AEO-27239-01 | DRILL R/H AFTER LOGO LIGHT SCREW(1EA) AT R/H H-STAB | 300 | NRM | EMP | GW | 3345 | 1 | 1 | COMP
VTL3129 | AEO-27239-01 | ALL LOGO LIGHT LENS SCREW CORROSION AND SCREW HOLDERS MISSING | 300 | NRM | EMP | AV | 3345 | 6 | 6 | COMP
VTL3137 | 777-53-862-00-01 | AFT CARGO AND BULK CGO FLOOR PANEL FND DIRTY | 100 | NRR | LWR | CL | 2500 | 10 | 10 | OPEN
VTL3145 | 777-53-862-00-01 | AFT CARGO ROLLER TRAY FND DIRTY | 100 | NRR | LWR | CL | 2500 | 16 | 16 | OPEN
VTL3152 | 777-53-824-00-01 | FWD CARGO FLOOR PANEL SURFACE FND DIRTY | 100 | NRR | LWR | CL | 2500 | 7 | 7 | OPEN
VTL3160 | 777-53-824-00-01 | FWD CARGO ROLLER TRAY FND DIRTY | 100 | NRR | LWR | CL | 2500 | 16 | 16 | OPEN
VTL3178 | 777-C252000-02-02-01 | ZONE D EY SEAT SEAT TRACK COVER FND BROKEN TTL:20EA | 200 | NRR | CAB | SS | 25 | 2 | 2 | OPEN
VTL3186 | 777-25-060-01-CX-01 | C/A SEAT PAN SPRING LOOSEN AT:L2FWD R3 L5 I/B TTL:3EA | 200 | NRP | CAB | SS | 25 | 3 | 3 | COMP
VTL3194 | 777-25-060-01-CX-01 | C/A SEAT DAMPENER FOUND WEAK AT:L3.R3.R4.L5 CTR I/B.R5 CTR I/B TTL:5EA | 200 | NRP | CAB | SS | 25 | 5 | 5 | WIP
VTL3202 | 777-25-060-01-CX-01 | C/A SEAT PAN DRESS COVER FOUND DIRTY AT:L3. R3.R4.L5 CTR I/B .R5 CTR I/B.R5 CTR O/B TTL:6EA | 200 | NRP | CAB | SS | 25 | 3 | 3 | COMP
VTL3210 | 777-25-060-01-CX-01 | C/A SEAT BACK REST LATCH FOUND MISSING AT:L5 CTR I/B L/R .L3 .R1. L1FWD L/R. R5 CTR I/B TTL:7EA | 200 | NRP | CAB | SS | 25 | 3.5 | 3.5 | OPEN
VTL3228 | 777-25-060-01-CX-01 | C/A SEAT UP BACK DRESS COVER FOUND DIRTY AT :L1FWD L2FWD L2AFT L3 R4 R5 CTR O/B TTL:6EA | 200 | NRP | CAB | SS | 25 | 3 | 3 | COMP
VTL3236 | 777-25-060-01-CX-01 | C/A SEAT PAN DRESS COVER FOUND TORN AT:L1FWD L1AFT R1 L2FWD R2 TTL:5EA | 200 | NRP | CAB | SS | 25 | 2.5 | 2.5 | COMP
VTL3244 | 777-25-060-01-CX-01 | C/A SEAT PAN SPRING FOUND BROKEN AT:L1FWD R5 CTR I/B TTL:2EA | 200 | NRP | CAB | SS | 25 | 4 | 4 | COMP
VTL3251 | AEO-29573-01 | CAB - PORTABLE OXY CYLINDER EXPIRY DATE LESS THAN 4.5 MONTHS LIFE REMAINED INSIDE LH CTR DOGHOUSE FWD OF LAV E (UPPER). | 200 | NRM | CAB | AV | 3531 | 1 | 1 | OPEN
VTL3269 | 777-25-060-02-CX-01 | C/A SEAT BELT FOUND FRAY AT:L1AFT R5 CTR I/B TTL:2EA | 200 | NRP | CAB | SS | 25 | 2 | 2 | WIP
VTL3277 | 777-25-060-02-CX-01 | C/A SEAT BELT SLIDE GUIDE FOUND CRACKED ATR1 R3 R4 L5 CTR O/B R5 CTR O/B AT:5EA | 200 | NRP | CAB | SS | 25 | 5 | 5 | WIP
VTL3285 | 777-25-060-01-CX-01 | C/A SEAT LOWER BACK DRESS COVER FOUND DIRTY AT:R1 L3 R3 R4 L5 CTR O/B R5 CTR I/B R5 CTR O/B TTL:7EA | 200 | NRP | CAB | SS | 25 | 3.5 | 3.5 | COMP
VTL3293 | 777-25-060-01-CX-01 | C/A SEAT HEADREST DRESS COVER FOUND DIRTY AT:L2FWD L3 R4 TTL:3EA | 200 | NRP | CAB | SS | 25 | 1.5 | 1.5 | COMP
VTL3301 | 777-C252440-04-01-01 | EY PAX SEAT PAN FOUND LOOSEN AT:53C 60D TTL:2EA | 200 | NRR | CAB | SS | 25 | 1 | 1 | COMP
VTL3319 | 777-C252440-04-01-01 | EY PAX SEAT LIFE VEST POUCH FOUND LOOSEN AT:56C 54E 50E 48E 46F 45F 44E 46H 69C 72D 69D 68E 65E 63E 64F 65F 67F 68F 69H TTL:19EA | 200 | NRR | CAB | SS | 25 | 14.5 | 14.5 | WIP
VTL3327 | 777-C252430-01-07-01 | PEY PAX SEAT BACKREST FOUND DISALIGNMENT:30ACDEFGHK 32ACDEFGHK 33ACDEFGHK TTL:12EA | 200 | NRR | CAB | SS | 2525 | 6 | 6 | OPEN
VTL3335 | 777-C252430-01-07-01 | PEY PAX SEAT BACKREST FOUND LOOSEN AT:30ACHK 32DEHK 33ACFG TTL:12EA | 200 | NRR | CAB | SS | 2525 | 6 | 6 | OPEN
VTL3343 | 777-C252430-01-07-01 | PEY PAX SEAT ARMREST FOUND LOOSEN AT:30CDGH 31CDGH 32CDGH 33CDGH TTL:16EA | 200 | NRR | CAB | SS | 2525 | 8 | 8 | OPEN
VTL3350 | AEO-29573-01 | CAB - PORTABLE OXY CYLINDER EXPIRY DATE LESS THAN 4.5 MONTHS LIFE REMAINED INSIDE LH CTR DOGHOUSE FWD OF GALLEY 4 (MID). | 200 | NRM | CAB | AV | 3531 | 1 | 1 | OPEN
VTL3368 | AEO-29573-01 | CAB - PORTABLE OXY CYLINDER EXPIRY DATE LESS THAN 4.5 MONTHS LIFE REMAINED INSIDE LH CTR DOGHOUSE FWD OF OFAR DOOR 5 (UPPER). | 200 | NRM | CAB | AV | 3531 | 1 | 1 | WIP
VTL3376 | 777-C252430-01-07-01 | PEY PAX SEAT IN ARM TABLE FOUND DISALIGNMENT AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK 33ACDEFGHK TTL:24 | 200 | NRR | CAB | SS | 2525 | 5.5 | 5.5 | OPEN
VTL3384 | 777-C252440-04-02-01 | EY PAX SEAT BACK TABLE FOUND DIRTY AT: 59A 60C 61B 65C 66C 69C 56A B 53F G 70C 67D E 64D E 53G 52H 65J TTL: 18EA | 200 | NRR | CAB | SS | 2525 | 9 | 9 | OPEN
VTL3392 | 777-55-850-02-01 | L/H AND R/H CAMERA SEALANT CRACKED | 300 | NRR | EMP | AV | 2410 | 4 | 4 | COMP
VTL3400 | 777-52-140-01-01 | M/D DR ARM COVER 3EA LWR VIEW PORT GLASS COVER FND MISSING | 200 | NRR | CAB | AI | 25 | 6 | 6 | COMP
VTL3418 | 777-900003-01-1-01 | NO.1 ENG FAN COWL, C-DUCT INNER SURFACE FOUND DIRTY | 400 | NRP | ENG | CL | 7100 | 8 | 8 | COMP
VTL3426 | 777-900003-01-1-01 | NO.2 ENG FAN COWL, C-DUCT INNER SURFACE FOUND DIRTY | 400 | NRP | ENG | CL | 7100 | 8 | 8 | COMP
VTL3434 | 777-53-880-00-01 | PLS DISCONNECT THE FUS LOWER FWD DRAIN MAST CONNECTIONS FOR ACC | 100 | NRR | FUS | AV | 53 | 0.01 | 0.01 | OPEN
VTL3442 | 777-53-553-00-01 | M/D PAX DR CUTOUT AND DR FRAME CUTOUT SOME STUD FND LOOSEN | 200 | NRR | CAB | AI | 25 | 4 | 4 | COMP
VTL3459 | 777-53-828-00-01 | CAB STA1035-1434 SEAT TRACK FND DIRTY. | 200 | NRR | CAB | CL | 2500 | 8 | 8 | COMP
VTL3467 | 777-53-920-00-01 | CABIN #5 DOOR K LAV AFT AREA TEDLAR FOUND SCRATCHED | 200 | NRR | CAB | SS | 25 | 0.01 | 16.01 | WIP
VTL3475 | 777-53-916-00-01 | CABIN #4 DOOD G4 GLY R/H AISLE S/W ARED TEDLAR FOUND SCRATCHED | 200 | NRR | CAB | SS | 2500 | 0.01 | 17.01 | WIP
VTL3483 | 777-C252430-01-04-01 | PEY PAX SEAT SIDE FAIRING SCREW PLUG FOUND MISSING AT:30AC 31AC 32AC 31G 32G 33G TTL:15EA | 200 | NRR | CAB | SS | 2525 | 3 | 3 | OPEN
VTL3491 | 777-C252430-01-04-01 | PEY PAX SEAT IN ARM TABLE ATT ARM CAP FOUND TORN AT:31G 32H TTL:2EA | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL3509 | 777-C252430-01-04-01 | PEY PAX SEAT ARM CAP FOUND TORN AT:30G 31G TTL:2EA | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL3517 | 777-C252430-01-07-01 | PEY PAX SEAT AFT LEGREST OPERATION FOUND LOOSEN AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK TTL:24EA | 200 | NRR | CAB | SS | 2525 | 6 | 6 | OPEN
VTL3525 | 777-C252430-01-07-01 | PEY PAX SEAT BACKREST BUTTON FOUND STIFF AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK 33ACDEFGHK TTL:32EA | 200 | NRR | CAB | SS | 2525 | 16 | 16 | WIP
VTL3533 | 777-C252430-01-07-01 | PEY PAX SEAT FOOTREST ATT SCREW FOUND LOOSEN AT:30ACDEFGHK TTL:8EA | 200 | NRR | CAB | SS | 2525 | 4 | 4 | OPEN
VTL3541 | 777-C252430-01-07-01 | PEY PAX SEAT LEGREST BUTTON FOUND STIFF AT:31ACHK 32DGHK 33ACFG TTL:12EA | 200 | NRR | CAB | SS | 2525 | 12 | 12 | OPEN
VTL3558 | 777-C252440-04-02-01 | EY PAX SEAT TABLE SLIDE FOUND JAMMED AT: 39HK 40HJK 43HJK-55HJK 39DEFG 40DEFG 41DEFG 43DEFG-54DEFG TTL: 101 | 200 | NRR | CAB | SS | 2525 | 20.2 | 20.2 | OPEN
VTL3566 | 777-54-824-01-01 | NO.1 PYLON 434BL FOUND 2EA ANCHOR NUT DMG | 400 | NRR | ENG | SM | 5400 | 2 | 2 | WIP
VTL3574 | 777-C252440-04-02-01 | EY PAX SEAT BACK SHROUD COAT HOOK FOUND MISSING AT: 68B,45D,54D | 200 | NRR | CAB | SS | 2525 | 1 | 1 | OPEN
VTL3582 | 777-C252430-01-04-01 | PEY PAX SEAT ASSY STRUCTURE ATT VELCRO TAPE FOUND PEEL OFF AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK TTL:32EA | 200 | NRR | CAB | SS | 2525 | 11 | 11 | WIP
VTL3590 | 777-55-864-02-01 | RIGHT H/STAB TIP FAIRING INNER SURFACE FOUND 1EA BONDING JUMPER CUT | 300 | NRR | EMP | AE | 5500 | 0.01 | 3.01 | COMP
VTL3608 | 777-C252440-04-02-01 | EY PAX SEAT BACK SHROUD COAT HOOK FOUND LOOSEN AT: 63J 68J 54D 61A 49H 54D 45D 40K TTL: 8EA | 200 | NRR | CAB | SS | 2525 | 3 | 3 | WIP
VTL3616 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER OPERATION FOUND JAMMED AT: 46A 47A B 51E 48D E F 46D E 47D 44E 43D 44D 41A 67D G 68E 69G 70E 61F G 70B C 45E 43A C TTL: 27EA | 200 | NRR | CAB | SS | 2525 | 6.75 | 6.75 | OPEN
VTL3624 | 777-C252430-01-04-01 | PEY PAX SEAT IN ARM TABLE STOWAGE VELCRO TAPE FOUND LOOSEN AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK 33ACDEFGHK TTL:32EA | 200 | NRR | CAB | SS | 2525 | 11 | 11 | OPEN
VTL3632 | 777-C252440-04-02-01 | EY PAX SEAT PAN ATT SEAL FOUND TORN AT:46C | 200 | NRR | CAB | SS | 25 | 1 | 1 | WIP
VTL3640 | 777-C252430-01-07-01 | PEY PAX SEAT IN ARM TABLE SLIDE FOUND STIFF AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK 33ACDEFGHK TTL:32EA | 200 | NRR | CAB | SS | 2525 | 5.5 | 5.5 | OPEN
VTL3657 | 777-C252430-01-07-01 | PEY PAX SEAT IN ARM TABLE FOUND LOOSEN AT:30ACDEFGHK 31ACDEFGHK 32ACDEFGHK 33ACDEFGHK TTL:32EA | 200 | NRR | CAB | SS | 2525 | 11 | 11 | OPEN
VTL3665 | 777-C252430-01-04-01 | PEY PAX SEAT PAN PIN& SCREW& WASHER FOUND WRONG AT 30A 31G TTL:6EA | 200 | NRR | CAB | SS | 2525 | 3 | 3 | COMP
VTL3673 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER OPERATION FOUND JAMMED AT: 61A 62A 66A 67A B 68C 69A B C G 62D 50K 48H J K 46J 45H J K 47H 44J K 43H J K 45B C TTL: 27EA | 200 | NRR | CAB | SS | 2525 | 6.75 | 6.75 | OPEN
VTL3681 | 777-53-904-00-01 | CAB-G8 GLY S1-0 1 COMPT DR TEDLAR FND DENT. | 200 | NRR | CAB | SS | 2500 | 0.01 | 10.01 | WIP | MHR changed to 10
VTL3699 | 777-C252430-01-04-01 | PEY PAX SEAT PAN SIDE COVER&BRACKET FOUND MISSING AT:30A | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL3707 | 777-C252430-01-01-01 | EY FIRST ROW SEAT IN ARM TABLE SHROUD TOP STOP STRIP FOUND BROKEN AT:39A.C 39E.F.G 40C 40H 43C 59C 59H TTL:10EA | 200 | NRR | CAB | SS | 25 | 5 | 5 | WIP
VTL3715 | 777-C252430-01-04-01 | PEY PAX SEAT PAN SIDE COVER& BRACKET ATT SCREW FOUND LOOSEN AT:32K | 200 | NRR | CAB | SS | 2525 | 1 | 1 | OPEN
VTL3723 | 777-C252000-01-09-R-03 | EY PAX SEAT BACKREST DRESS COVER FND DIRTY TTL: 216EA | 200 | NRR | CAB | SS | 25 | 0.1 | 0.1 | OPEN
VTL3731 | 777-C252000-01-09-R-03 | EY PAX SEAT BOTTOM DRESS COVER FND DIRTY TTL: 222EA | 200 | NRR | CAB | SS | 25 | 0.1 | 0.1 | OPEN
VTL3749 | 777-55-864-02-01 | BOTH H/STAB LE ACC PNLS UPPER AND LOWER EDGE FOUND PAINT IRREGULAR | 300 | NRR | EMP | SS | 5500 | 0.01 | 24.02 | WIP
VTL3756 | 777-C252000-01-09-R-03 | EY PAX SEAT BOTTOM DRESS COVER FND TORN TTL: 12EA | 200 | NRR | CAB | SS | 25 | 4 | 4 | OPEN
VTL3764 | 777-C330000-01-01-01 | CAB - CEILING LIGHT FOUND LAMP OFF ABOVE SEAT 32ABC. | 200 | NRR | CAB | AV | 3321 | 1 | 1 | WIP
VTL3772 | 777-C252000-01-09-R-03 | EY PAX SEAT BOTTOM DRESS COVER FND NOT MATCH TTL: 62EA | 200 | NRR | CAB | SS | 25 | 21 | 21 | OPEN
VTL3780 | 777-C330000-01-01-01 | CAB - LAV DOME LIGHT FOUND LAMP OFF AT LAV C, E, J. | 200 | NRR | CAB | AV | 3321 | 1 | 1 | WIP
VTL3798 | TA28000101 | AT FUEL TANK PANEL - 633FB, FOUND MEASURING STICK TUBE DAMAGE. | 600 | NRR | F/T | AE | 2800 | 0.01 | 8.01 | WIP
VTL3806 | 777-900001-01-1-01 | NO.1 ENG EDP FOUND HYD LEAK IN CONTROL SOLENOID AREA | 400 | NRP | ENG | AE | 7100 | 0.01 | 27.01 | WIP
VTL3814 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER FOUND CRACKED AT51F 56A 50A B 49A 47A B 46B 45B C 44A B C 40A B 39A C 63C TTL: 18EA | 200 | NRR | CAB | SS | 2525 | 9 | 9 | WIP
VTL3822 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER FOUND CRACKED AT66B C 67C 68A 69A 70A 50K 45H 44K 43K 39H D F G 40F 41F 47F G 49F G TTL: 20EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | WIP
VTL3830 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER FOUND CRACKED AT: 52D G 53D 54D 53D 52K 62H 63K 67K 71D 70D 59A B 60A B 61A B 62A 64A B TTL: 20EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | WIP
VTL3848 | 777-C252000-01-07-R-02 | B/C PAX SEAT HEADREST ATT FROM FOUND MISSING ( P/N:F0419548) TTL:2EA | 200 | NRR | CAB | SS | 2525 | 0.5 | 0.5 | OPEN
VTL3855 | 777-C252000-01-08-R-02 | PEY PAX SEAT HEADREST SIDE SCREW FOUND MISSING AT:32G 33H TTL:4EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | OPEN
VTL3863 | 777-C252000-01-08-R-02 | PEY PAX SEAT UP ATT BRACKET FOUND MISSING AT:32AC TTL:2EA | 200 | NRR | CAB | SS | 2525 | 1 | 1 | OPEN
VTL3871 | 777-C252000-01-08-R-02 | PEY PAX SEAT TV SHROUD UP SCREW FOUND MISSING AT:31ACDEFGHK TTL:16EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | OPEN
VTL3889 | 777-C252430-01-01-01 | EY FIRST ROW SEAT SIDE BUMPER FOUND LOOSEN AT:39H | 200 | NRR | CAB | SS | 25 | 2 | 2 | WIP
VTL3897 | 777-C252000-01-08-R-02 | PEY PAX SEAT TV SHROUD LOWER SCREW FOUND MISSING AT:30ACDEFGHK 31ACDEFGHK TTL:32EA | 200 | NRR | CAB | SS | 2525 | 4 | 4 | OPEN
VTL3905 | 777-C252430-01-01-01 | EY FIRST ROW SEAT IN ARM TABLE FOUND MIS -ALIGN AT:39AC 39DG 39HK 43AC 43DG 43HK 59AC 60DG 59HK TTL:9EA | 200 | NRR | CAB | SS | 25 | 7 | 7 | WIP
VTL3913 | 777-C252430-01-01-01 | EY FIRST ROW SEAT TV ARM FOUND UNLOCK AT:59H | 200 | NRR | CAB | SS | 25 | 2 | 2 | WIP
VTL3921 | 777-C252440-04-02-01 | EY PAX SEAT TABLE FOUND DISALIGNMNT AT: 39AC 40ABC 41ABC 43ABC-56ABC 59ABC-70ABC TTL: 87EA | 200 | NRR | CAB | SS | 2525 | 21.5 | 21.5 | OPEN
VTL3939 | 777-C252430-01-01-01 | EY FIRST ROW SEAT ARM CAP SCREW FOUND LOOSEN AT:59HJ | 200 | NRR | CAB | SS | 25 | 1 | 1 | WIP
VTL3947 | 777-C252440-04-02-01 | EY PAX SEAT TABLE FOUND DISALIGNMNT AT: 39DEFG 40DEFG 41DEFG 43DEFG-54DEFG 59DEFG-67DEFG 68EFG 69DEG 70DEG 71DEG TTL: 84EA | 200 | NRR | CAB | SS | 2525 | 35 | 35 | WIP
VTL3954 | 777-C252440-04-02-01 | EY SEAT LITERATURE POCKET FND DIRTY AT: 39A 40A 41A 43A C 44A C 45A C 46B C 47A 49A B 50B 51C 53B C 54A B C 56A B C 59A B 60A 61B C 62A B 63C 64A C 65A B 66A C 67C 68A TTL:40EA | 200 | NRR | CAB | SS | 25 | 8 | 8 | WIP
VTL3962 | 777-C252430-01-01-01 | EY FIRST ROW SEAT SIDE FAIRING SCREW FOUND LOOSEN AT:39D 43G TTL:2EA | 200 | NRR | CAB | SS | 25 | 1 | 1 | WIP
VTL3970 | 777-C252430-01-01-01 | EY FIRST ROW SEAT ARMREST TIRM CAP FOUND LOOSEN AT:39D 60DE TTL:2EA | 200 | NRR | CAB | SS | 25 | 2 | 2 | OPEN
VTL3988 | 777-C252430-01-04-01 | PEY PAX SEAT CTR CONSOLE ATT PANEL FOUND LOOSEN AT:30G | 200 | NRR | CAB | SS | 2525 | 2 | 2 | OPEN
VTL3996 | 777-C252430-01-01-01 | EY FIRST ROW SEAT SIDE BAY BRACKET FOUND BROKEN AT:39D 60D.G TTL:3EA | 200 | NRR | CAB | SS | 25 | 6 | 6 | WIP
VTL4002 | 777-C252430-01-04-01 | PEY PAX SEAT IN ARM TABLE STOWAGE SHROUD FOUND CRACK AT:31H | 200 | NRR | CAB | SS | 2525 | 0.5 | 0.5 | COMP
VTL4010 | 777-C252440-04-01-01 | EY PAX SEAT SEAT PAN SEAL FOUND TORN AT:39D | 200 | NRR | CAB | SS | 25 | 1 | 1 | COMP
VTL4028 | 777-C252430-01-04-01 | PEY PAX SEAT IN ARM TABLE TRAY FOUND PEEL OFF AT:30A 30K | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL4036 | 777-C252430-01-01-01 | EY FIRST ROW SEAT IN TABLE SHROUD FOUND BROKEN AT:43D.E.F.G 43H.J.K 60D.E.F.G 59H.JK. TTL:14EA | 200 | NRR | CAB | SS | 25 | 14 | 14 | WIP
VTL4044 | 777-C252440-04-02-01 | EY PAX SEAT TABLE SLIDE FOUND JAMMED59DEFG-67DEFG 68EFG 69DEG 70DEG 71DEG 59HJK-70HJK TTL: 80EA | 200 | NRR | CAB | SS | 2525 | 16 | 16 | WIP
VTL4051 | 777-C252430-01-04-01 | PEY PAX SEAT ARMREST LOWER BIG PLUG FOUND MISSING AT:30A 31A 32A 33A 30K 31K 33K TTL:7EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | COMP
VTL4069 | 777-C252430-01-04-01 | PEY PAX SEAT ARMREST LOWER SMALL PLUG FOUND MISSING AT:33D 32D 30AC 33A 30G 31G 33K 30HK TTL:15EA | 200 | NRR | CAB | SS | 2525 | 3 | 3 | COMP
VTL4077 | 777-C252430-01-01-01 | EY FIRST ROW SEAT IN ARM TABLE SHROUD FOUND BROKEN AT:39A.C 39D.E.F.G 40C 39H 40H 43A.B.C 59A.B.C TTL:15EA | 200 | NRR | CAB | SS | 25 | 15 | 15 | WIP
VTL4085 | 777-C252430-01-04-01 | PEY PAX SEAT PAN FOUND BROKEN AT:31G | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL4093 | 777-C252430-01-04-01 | PEY PAX SEAT CTR CONSOLE AFT LOWER SCREW& WASHER FOUND MISSING AT:30DE FG HK TTL:10EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | WIP
VTL4101 | 777-C252430-01-01-01 | EY FIRST ROW SEAT IN ARM TABLE OPERATION FOUND TIGHTEN AT:43B.C 59A.B.C 60D.E.G TTL:8EA | 200 | NRR | CAB | SS | 25 | 8 | 8 | WIP
VTL4119 | 777-C252430-01-01-01 | EY FIRST ROW SEAT TV ARM FOUND LOOSEN AT:43A | 200 | NRR | CAB | SS | 25 | 2 | 2 | COMP
VTL4127 | 777-C252430-01-01-01 | EY FIRST ROW SEAT SIDE FIRING FOUND CRACKED AT:60D 43C TTL:2EA | 200 | NRR | CAB | SS | 25 | 4 | 4 | WIP
VTL4135 | 777-C252440-04-02-01 | EY PAX SEAT TABLE SLIDE FOUND JAMMED39AC 40ABC 41ABC 43ABC-56ABC 59ABC-70 ABC TTL: 84EA | 200 | NRR | CAB | SS | 2525 | 16.8 | 16.8 | WIP
VTL4143 | 777-C252430-01-01-01 | EY FIRST ROW SEAT ARM CAP FOUND BROKEN AT:43DE G TTL:2EA | 200 | NRR | CAB | SS | 25 | 2 | 2 | COMP
VTL4150 | 777-C252440-04-02-01 | EY PAX SEAT TABLE FOUND DISALIGNMENT AT: 39HK 40HJK 43HJK-54HJK 59HJK-70HJK TTL: 78EA | 200 | NRR | CAB | SS | 2525 | 19.5 | 19.5 | OPEN
VTL4168 | 777-C252430-01-01-01 | EY FIRST ROW SEAT IN ARM TABLE FACE FOUND SCRATCHED AT:43G | 200 | NRR | CAB | SS | 25 | 1 | 1 | WIP
VTL4176 | 777-C252430-01-01-01 | EY FIRST ROW SEAT UP SIDE FIRING FOUND CRACKED AT:60G | 200 | NRR | CAB | SS | 25 | 2 | 2 | OPEN
VTL4184 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST SCREW ATT PLUG FOUND MISSING AT:63HJ 65HJ 72DE 71D DE 70EG 65FG 64DE 62DE 63A TTL:10EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | OPEN
VTL4192 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER ATT COVER FOUND MISSING AT: 65G | 200 | NRR | CAB | SS | 2525 | 1 | 1 | OPEN
VTL4200 | 777-C252440-04-02-01 | EY PAX SEAT PED HOLDER LOWER COVER FOUND LOOSE AT: 41G | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL4218 | 777-C252440-04-02-01 | EY PAX SEAT BACK TABLE LATCH FOUND JAMMED AT: 59A B C 60A B C 61A B C 62A B C 63A B C 64A C 65A B 66A B C 67A B 68A B C 69C 56A C TTL: 30EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | WIP
VTL4226 | 777-C252440-04-02-01 | EY SEAT LITERATURE POCKET FND DIRTY AT: 43D E 44E 45E 46D E 49D 50D E 51D 54E 61E 63E 64D 70D E 71D 39F 40F G 41F 43F 44G 45F G 46F 47F 48F 50G 51F 54F G 60F G 61F 62F 63F 64G 66F G TTL:40EA | 200 | NRR | CAB | SS | 25 | 8 | 8 | WIP
VTL4234 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST SCREW ATT PLUG FOUND MISSING AT:65BC 67A 69BC 54EF 55EF 41JK 46JK 48JK 51HJ 49HJ TTL:10EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | OPEN
VTL4242 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST SCREW ATT PLUG FOUND MISSING AT:51FG 48EF 47FG 46DE 45DE 44FG 43EF 42D 41FG 40FG TTL10EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | OPEN
VTL4259 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST LOWER COVER FOUND MISSING AT:48HJ 69BC 60AB TTL:3EA | 200 | NRR | CAB | SS | 2525 | 1.5 | 1.5 | WIP
VTL4267 | 777-C252440-04-04-01 | EY PAX SEAT ARM CAP FOUND LOOSEN AT:70C | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL4275 | 777-C252440-04-02-01 | EY PAX SEAT BACK TABLE LATCH FOUND JAMMED AT:71D E G 69D E G51K 50H K 48H 46H 43A C 45C 46A 48F A 49A 54G D B C 55A 44D 67D E 62D E 54H J 52J 54D G 59J K TTL: 35EA | 200 | NRR | CAB | SS | 2525 | 11 | 11 | WIP
VTL4283 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST SCREW ATT PLUG FOUND MISSING AT:40G 40AB 46C 49AB 53C 55AB 55BC 56BC 57AB TTL: | 200 | NRR | CAB | SS | 2525 | 2 | 2 | WIP
VTL4291 | 777-C252440-04-03-01 | EY PAX SEAT RECLINE BUTTON FOUND STIFF AT:48C 63K | 200 | NRR | CAB | SS | 2522 | 2 | 2 | COMP
VTL4309 | 777-C252440-04-02-01 | EY PAX SEAT BACK TABLE FOUND LOOSE AT: 60K 63H J K 64H 65J 53K 52F 59B 66B 69C 70A D 67G 64K TTL: 15EA | 200 | NRR | CAB | SS | 2525 | 4 | 4 | OPEN
VTL4317 | 777-C252440-04-04-01 | EY PAX SEAT TRIM CAP FOUND LOOSEN AT:46C 62AB TTL:2EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | COMP
VTL4325 | 777-C252440-04-02-01 | EY SEAT LITERATURE POCKET FND DIRTY AT: 67G 68G 70F G 71G 43H J 40H 45H K 46H 48H J 49H J K 50K 52J 54J 59J K 60H J 61J 63J K 64H 65K 66H 67J K 68H J 70H J K TTL:36EA | 200 | NRR | CAB | SS | 25 | 7.2 | 7.2 | WIP
VTL4333 | 777-C252000-01-02-01 | M/D D. E ZONE UNDER SEAT ALL REMOVED FLOOR CARPETS AREA FLOOR PNL SURFACE FND RESIDUAL DOUBLE TYPE. | 200 | NRP | CAB | CL | 2527 | 60 | 60 | COMP
VTL4341 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST REAR COVER FOUND MISSING AT:44A 59K TTL:2EA | 200 | NRR | CAB | SS | 2525 | 2 | 2 | COMP
VTL4358 | 777-C252440-04-02-01 | EY SEAT LITERATURE POCKET FND NOT MATCH AT: 44K 46K 49F 40D 41G 45B 46C 48C 50C 52F G 63G 64E 65E TTL:14EA | 200 | NRR | CAB | SS | 25 | 7 | 7 | WIP
VTL4366 | 777-20-766-00-01 | CABIN D ZONE LH & RH DADO PANELS FOUND DIRTY | 200 | NRR | CAB | CL | 2500 | 8 | 8 | COMP
VTL4374 | 777-20-766-00-01 | CABIN C ZONE LH & RH DADO PANELS FOUND DIRTY | 200 | NRR | CAB | CL | 2500 | 8 | 8 | COMP
VTL4382 | 777-C252440-04-02-01 | EY SEAT LITERATURE POCKET FND LOOSEN AT: 59C 62A B C 40K 44K 45H 48K 49H 50H 51K E 50F 48D E G 47G 44E 43E 41E 40D F G 41A 40A 44A 47A 49A B C 56A B 54J 60F 61D K 63K 65H K 67K 70J K E C 69A C 68C 67A 65A B 62A C TTL:52EA | 200 | NRR | CAB | SS | 25 | 5 | 5 | OPEN
VTL4390 | 777-C252440-04-02-01 | EY SEAT SEAT PAN LOWER PANEL FND LOOSEN AT: 66A | 200 | NRR | CAB | SS | 25 | 0.5 | 0.5 | WIP
VTL4408 | 777-C252440-04-04-01 | EY SEAT SIDE BUMPER FND BROKEN AT: 51G 70H 66C 51C 50D 49D 46D 49C TTL: 8EA | 200 | NRR | CAB | SS | 25 | 2 | 2 | OPEN
VTL4416 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST ARM CAP ATT COVER FOUND MISSING AT:45D | 200 | NRR | CAB | SS | 2525 | 1 | 1 | COMP
VTL4424 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST OPERATION FOUND LOOSEN AT:67A 68C 69BC 70G 67D 66D 63D 59K 61K 62H 62K 63H 63K 66K TTL: | 200 | NRR | CAB | SS | 2525 | 7 | 7 | WIP
VTL4432 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST OPERATION FOUND LOOSEN AT:42D 42G 44A 45AB 49A 49AB 54A 55A 52G 52DE 48D 48G 46EF 48K 54K 63A 64A 66BC TTL:18EA | 200 | NRR | CAB | SS | 2525 | 9 | 9 | WIP
VTL4440 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST LOWER COVER FOUND LOOSEN AT:42D 44C 48C 55D 50G 49G 47D 45C 45FG 44H 46H 49JK 49H 51H 68C 71G 70G 65G 63D 62G TTL:20EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | OPEN
VTL4457 | 777-C252440-04-04-01 | EY SEAT SIDE FAIRING FND BROKEN AT: 43G 44H 59H 59C 55G TTL: 5EA | 200 | NRR | CAB | SS | 25 | 10 | 10 | WIP
VTL4465 | 777-53-908-00-01 | CAB - DOOR 2L SERVICE OUTLET COVER FOUND DAMAGE. | 200 | NRR | CAB | AV | 2524 | 1 | 1 | WIP
VTL4473 | 777-53-908-00-01 | CAB - DOOR 2R EXIT SIGN BOTH HOUSING STOPPER FOUND DAMAGE. | 200 | NRR | CAB | AV | 2524 | 1 | 1 | WIP
VTL4481 | 777-29-000-02-CX-01 | ALL HYD SYS ACMP EDP ADP FILTERS MODULE FND DPI INDICATION DUST CAPS (16EA) AGED | 100 | NRP | FUS | AE | 32 | 6 | 6 | COMP
VTL4499 | 777-53-892-00-01 | FUS LOWER ACC PNL INTERNAL SURFACE FND DIRTY | 100 | NRR | FUS | CL | 53 | 10 | 10 | COMP
VTL4507 | 777-53-894-00-01 | RH AFT WING TO BODY FAIRING PNL198PR FND ANCHOR NUTS (4EA)BROKEN | 100 | NRR | FUS | SM | 53 | 0.01 | 3.01 | WIP
VTL4515 | 777-53-926-00-01 | APPLY CIC TO THE ACC PNLS 311BL AND 313AL CAVIRY | 300 | NRR | EMP | AE | 5500 | 4 | 4 | OPEN
VTL4523 | AEO-25413-01 | INSTALL THE RUDDER PCP ACC PNL FOR PT PAINTING | 300 | PNT | EMP | AE | 2700 | 0 | 0 | OPEN | For maintenance only, No charge to CX
VTL4531 | 777 BASIC CLOSE 500 | FOUND MANY SCREWS HEAD WORN, AT LHW L/E AND T/E ACCESS PANEL. | 500 | NRR | WNG | AE | 5700 | 1 | 1 | OPEN
VTL4549 | AEO-25413-01 | INSTALL THE BOTH ELE PCP ACC PNLS FOR PT PAINTING | 300 | PNT | EMP | AE | 5500 | 0 | 0 | WIP | For maintenance only, No charge to CX
VTL4556 | 777 BASIC CLOSE 600 | FOUND MANY SCREWS HEAD WORN, AT RHW L/E AND T/E ACCESS PANEL. | 500 | NRR | WNG | AE | 5700 | 1 | 1 | OPEN
VTL4564 | 777-32-000-02-CXNA-01 | MEC LANDING GEAR DOWN LOCK PIN RED WARNING STREAMER FOUND DIRTY. TTL 5EA | 100 | NRP | LWR | AI | 3200 | 5 | 5 | COMP
VTL4572 | 777-53-818-00-01 | FWD CGO STA804-825+210 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | WIP
VTL4580 | 777-53-818-00-01 | FWD CGO STA825+210-1035 L/H & R/H SIDE WALL AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | WIP
VTL4598 | 777-53-818-00-01 | FWD CGO STA409-613 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | WIP
VTL4606 | 777-53-818-00-01 | FWD CGO STA613-804 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | WIP
VTL4614 | 777-53-818-00-01 | FWD CGO STA804-825+210 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 7 | 7 | WIP
VTL4622 | 777-53-818-00-01 | FWD CGO STA825+210-1035 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 7 | 7 | WIP
VTL4630 | AEO-25413-01 | FUS LOWER SKIN FOUND 12EA DRAIN V/V IN POOR CONDITION | 100 | PNT | FUS | AE | 5300 | 3 | 3 | OPEN
VTL4648 | 777-25-040-03-CX-01-01 | CAB - FB2 SEATS EMA SERVICE LIFE DATE FOUND EXPIRED. | 200 | NRR | CAB | AV | 2502 | 80 | 80 | OPEN
VTL4655 | 777-32-000-02-CXNA-01 | MEC MAIN LANDING GEAR DOWN LOCK PIN 1EA LANYARD (P/N 50996-38W) FOUND BROKEN | 100 | NRP | LWR | AI | 3200 | 2 | 2 | COMP
VTL4663 | 777-53-920-00-01 | M/D L/R 5 DOOR FUSELAGE EDGE FND PAINT CHIP | 200 | NRR | CAB | PT | 5121 | 6 | 6 | WIP
VTL4671 | 777-C252500-01-04-01 | M/D L/R 4 DOOR FUSELAGE EDGE FND PAINT CHIP | 200 | NRR | CAB | PT | 5121 | 6 | 6 | OPEN
VTL4689 | 777-53-904-00-01 | M/D A LAV DOOR INTERIOR BLACK LINE PAINT CHIP | 200 | NRR | CAB | PT | 2500 | 0.5 | 0.5 | OPEN
VTL4697 | 777-53-904-00-01 | M/D C-102 C-103 R-202 GALLEY DOOR INTERIOR SURFACE FND PAINT CHIP | 200 | NRR | CAB | PT | 2500 | 6 | 6 | OPEN
VTL4705 | 777-900003-01-1-01 | 1ST OBS SEAT LUMBER SUPPORT FND NOISE | 200 | NRP | CAB | SS | 2511 | 2 | 2 | WIP
VTL4713 | 777-900003-01-1-01 | 1ST OBS SEAT BACK COVER FND LOOSE | 200 | NRP | CAB | SS | 2511 | 1 | 1 | OPEN
VTL4721 | 777-900003-01-1-01 | 1ST OBS SEAT TABLE PANEL FND MISSING | 200 | NRP | CAB | SS | 2511 | 2 | 2 | OPEN
VTL4739 | 777-53-526-00-01 | AFT CGO DOOR ARM SUPPORT FND PAINT CHIP | 100 | NRR | LWR | PT | 5121 | 2 | 2 | OPEN
VTL4747 | 777-53-509-01-01 | FWD CGO DOOR ARM SUPPORT FND PAINT CHIP | 100 | NRR | LWR | PT | 5121 | 2 | 2 | OPEN
VTL4754 | 777-53-509-01-01 | FWD CGO DOOR DEPRESSOR SEAL FOUND PAINT CHIP | 100 | NRR | LWR | PT | 5121 | 6 | 6 | OPEN
VTL4762 | 777-53-526-00-01 | AFT CGO DOOR DEPRESSOR SEAL FOUND PAINT CHIP | 100 | NRR | LWR | PT | 5121 | 6 | 6 | OPEN
VTL4770 | 777-53-862-00-01 | AFT CGO STA1643-1886 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | OPEN
VTL4788 | 777-53-874-00-01 | BULK CGO STA1886-2062 BILGE AREA INSULATION BLANKET FOUND TORN | 100 | NRR | LWR | AI | 2500 | 6 | 6 | OPEN
VTL4796 | 777-C254000-01-02-01A | CAB LAV F TOILET SHROUD FLAP DAMPER FND WEAK | 200 | NRR | CAB | AI | 25 | 2 | 2 | COMP
VTL4804 | 777-900003-01-1-01 | FOUND 40A SIDEWALL LIGHT INOP | 200 | NRP | CAB | AV | 33 | 1 | 1 | WIP
VTL4812 | 777-C252430-01-06-01 | PEY SEAT SEAT BACK TV SHROUD FND BROKEN AT: 31A | 200 | NRR | CAB | SS | 25 | 0.5 | 0.5 | OPEN
VTL4820 | 777-53-854-00-01 | FWD CGO STA529 R/H CEILING AREA 2EA STAND OFF FOUND DAMAGED | 100 | NRR | LWR | SM | 2500 | 0.01 | 6.51 | WIP
VTL4838 | 777-53-920-00-01 | CABIN G6/7 GLY COMPARTMENT DOOR EDGE CAUTION TAPE FOUND WORN | 200 | NRR | CAB | AI | 2500 | 3 | 3 | OPEN
VTL4846 | 777-53-874-00-01 | BULK CGO STA1920-2060 FLR AREA 7EA ANCHOR NUT FOUND DAMAGED | 100 | NRR | LWR | SM | 5300 | 0.01 | 5.01 | WIP
VTL4853 | 777-53-920-00-01 | CABIN B ZONE RH NO.7 PAX WINDOW INNER REVEAL FOUND CRACK | 200 | NRR | CAB | AI | 2500 | 1 | 1 | COMP
VTL4861 | 777-25-050-02-CX-R-01 | PEY PAX SEAT DRESS COVER FOUND TORN TTL:18EA | 100 | NRR | CAB | SS | 2525 | 2.5 | 2.5 | OPEN
VTL4879 | 777-25-050-02-CX-R-01 | PEY PAX SEAT DRESS COVER FOUND NOT MATCH TTL:8EA | 200 | NRR | CAB | SS | 2525 | 1 | 1 | OPEN
VTL4887 | 777-C252000-01-07-R-02 | B/C PAX SEAT DRESS COVER FOUND TORN TTL:51EA | 200 | NRR | CAB | SS | 25 | 5 | 5 | OPEN
VTL4895 | 777-C252000-01-02-01 | PAX SEAT TRACK COVER FOUND DIRTY | 200 | NRP | CAB | SS | 2525 | 8 | 8 | OPEN
VTL4903 | 777-C252000-01-07-R-02 | B/C PAX SEAT RECLINE BUTTON FOUND DAMAGE AT:16K 20D 21D 18D | 200 | NRR | CAB | SS | 2525 | 4 | 4 | OPEN
VTL4911 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:67H69J70H70J70K71H TTL:6EA | 200 | NRR | CAB | SS | 2525 | 6 | 6 | OPEN
VTL4929 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:61D60D60E60G62H62J64H64J66H66K TTL:10EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | OPEN
VTL4937 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:64A64B66C70A71B71G67G67E65G64D TTL:10EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | OPEN
VTL4945 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:52J53H54J54H55K59A60A61A61C62A | 200 | NRR | CAB | SS | 2525 | 10 | 10 | OPEN
VTL4952 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:44H45J45K46H46J47H49J50H50J50K TTL10EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | WIP
VTL4960 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:54A 54B 56A 54E 54F 53E 46D 43D 43E 44K TTL:10EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | OPEN
VTL4978 | 777-C252440-04-03-01 | EY PAX SEAT HYD FOUND MALFUNCTION AT:40J 40K 41D 41G 40F 39D 39E 41A 45B 52A TTL:10EA | 200 | NRR | CAB | SS | 2525 | 10 | 10 | OPEN
VTL4986 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST ARM CAP FOUND BROKEN AT:55G 45D 62AB 62BC 63BC 70BC 66DE 65D 63EF 60AB TTL:10EA | 200 | NRR | CAB | SS | 2525 | 5 | 5 | WIP
VTL4994 | 777-C252440-04-04-01 | EY PAX SEAT ARMREST ARM CAP FOUND BROKEN AT:42G 41FG 41DE 40AB 40G 45BC 47A 48AB 53BC 56AB TTL:10EA | 200 | NRR | CAB | SS | 2525 | 5 | 5 | WIP
VTL5009 | 777-900001-01-1-01 | AT NO 1 ENGINE 2EA SEPARATOR FOR FEEDER CABLE MISSING | 400 | NRP | ENG | AV | 2410 | 2 | 2 | OPEN
VTL5017 | 777-900003-01-1-01 | NO.1 ENG L/H UPPER OGV FAIRING FOUND 1EA ANCHOR NUT DMG | 400 | NRP | ENG | SM | 7100 | 0.01 | 12.01 | WIP
VTL5025 |  | REFER TO CANNIBALIZATION FORM VT001 ITEM 1 - REMOVE 1EA BALLAST P/N:8184-1 MODA S/N:245425 IN G6-G7 LOWER CEILING PNL FROM B-KQX TO SUPPORT B-KPO. | 200 | CAN | CAB | AI | 25 | 0.01 | 0.01 | OPEN
VTL5033 | 777-53-818-00-01 | FWD CGO STA998 END WALL DIVIDER NET FASTENER FOUND DAMAGED TTL 8EA | 100 | NRR | LWR | SS | 2500 | 0.01 | 0.01 | OPEN
VTL5041 |  | REFER TO CANNIBALIZATION FORM VT001 ITEM 2 - REMOVE 1EA BALLAST P/N:8184-1 MODA S/N:245416 IN G6-G7 LOWER CEILING PNL FROM B-KQX TO SUPPORT B-KPO. | 200 | CAN | CAB | AI | 25 | 0.01 | 0.01 | OPEN
VTL5058 |  | REFER TO CANNIBALIZATION FORM VT001 ITEM 3 - REMOVE 1EA BALLAST P/N:8184-1 MODA S/N:205180 IN G6-G7 LOWER CEILING PNL FROM B-KQX TO SUPPORT B-KPO. | 200 | CAN | CAB | AI | 25 | 0.01 | 0.01 | OPEN
VTL5066 | 777-12-080-00-R-01 | LH MLG DRAG AND SIDE BRACE LOCK LINK FND GREASE FITTINGS (5EA) MISSING | 700 | NRP | LDG | AE | 32 | 5 | 5 | COMP
VTL5074 |  | REFER TO CANNIBALIZATION FORM VT001 ITEM 4 - REMOVE 1EA LIGHT ASSY P/N:3352-90-13500 S/N:040488 IN 39AC SW LT FROM B-KQX TO SUPPORT B-KPO. | 200 | CAN | CAB | AV | 33 | 0.01 | 0.01 | WIP
VTL5082 | 777-12-080-00-R-02 | RH MLG DRAG AND SIDE BRACE LOCK LINK FND GREASE FITTINGS 6EA MISSING | 700 | NRP | LDG | AE | 32 | 3 | 3 | COMP
VTL5090 |  | REFER TO CANNIBALIZATION FORM VT001 ITEM 5 - REMOVE 1EA OEU P/N:285W0029-4 S/N:103085 IN 12G FROM B-KQX TO SUPPORT B-KPO. | 200 | CAN | CAB | AV | 23 | 0.01 | 0.01 | WIP
VTL5108 | 777-25-050-02-CX-R-01 | EY PAX SEAT BACKREST DRESS COVER FOUND NOT MATCH TTL:4EA | 200 | NRR | CAB | SS | 2525 | 1 | 1 | OPEN
VTL5116 | 777-25-050-02-CX-R-01 | EY PAX SEAT BACKREST DRESS COVER FOUND TORN TTL:46EA | 200 | NRR | CAB | SS | 2525 | 4 | 4 | OPEN
VTL5124 | 777-53-920-00-01 | CABIN #5 DOOR CREW REST AFT AREA TEDLAR FOUND SCRATCHED | 200 | NRR | CAB | SS | 25 | 0.01 | 16.01 | WIP
VTL5132 | 777-53-902-00-01 | COCKPIT - L3 WINDOW WIRE TERMINAL BLOCK J9 FOUND DETACHED. | 200 | NRC | CAB | AI | 5611 | 0.01 | 0.01 | OPEN
VTL5140 | 777-53-812-00-01 | FEC COMPARTMENT INTERIOR FOUND DIRTY | 100 | NRR | LWR | CL | 2500 | 3 | 3 | COMP
VTL5157 | 777-53-818-00-01 | FWD CARGO CEILING PANEL SURFACE FND DIRTY | 100 | NRR | LWR | CL | 2500 | 7 | 7 | WIP
VTL5165 | 777-53-818-00-01 | FWD CARGO SIDEWALL PANEL SURFACE FND DIRTY | 100 | NRR | LWR | CL | 2500 | 7 | 7 | WIP
VTL5173 | 777-53-854-00-01 | AFT CARGO CEILING PANEL SURFACE FND DIRTY | 100 | NRR | LWR | CL | 2500 | 7 | 7 | WIP
VTL5181 | 777-53-854-00-01 | AFT CARGO SIDEWALL PANEL SURFACE FND DIRTY | 100 | NRR | LWR | CL | 2500 | 7 | 7 | OPEN
VTL5199 | 777-53-870-00-01 | BULK CARGO COMP CEILING AND SIDEWALL PANEL FND DIRTY | 100 | NRR | LWR | CL | 2500 | 5 | 5 | OPEN
VTL5207 | 777-900003-01-1-01 | FOUND G6 G7 GALLEY LOWER CEILING PANEL FWD 4EA CEILING LIGHT BALLAST MALFUNCTION | 200 | NRP | CAB | AV | 3327 | 4 | 4 | OPEN
VTL5215 | 777-57-954-02-01 | RHW FLAPERON, I/B SIDE, 4 EA SEAL WORN, 1 EA SEAL DETACHED. | 600 | NRR | WNG | AE | 5700 | 6 | 6 | WIP
VTL5223 | 777-57-954-02-01 | RHW FLAPERON LIP DOOR, TOTAL 3 EA SEAL WORN. | 600 | NRR | WNG | AE | 5700 | 6 | 6 | COMP
VTL5231 | 777-57-862-01-01 | LHW FLAPERON, I/B SIDE, 2 EA SEAL WORN, 1EA SEAL DETACHED. | 500 | NRR | WNG | AE | 5700 | 4 | 4 | WIP
VTL5249 | 777-57-862-01-01 | LHW FLAPERON, O/B SIDE, UPPER SEAL WORN. | 500 | NRR | WNG | AE | 5700 | 2 | 2 | OPEN
VTL5256 | 777-57-910-02-01 | LHW L/E SLATS FROM NO.1 TO NO.7, FOUND THE SKIRT PANEL PAINT IRREGULARITIES | 500 | NRR | WNG | SS | 5743 | 0.01 | 34.02 | WIP | Will change to 30mhr
VTL5264 | 777 BASIC CLOSE 500 | FOUND MANY ANCHOR NUTS DAMAGE ,NEEDED REPLACE, AT BOTH WING L/E PANEL: 621JB,621MB,521RB,521YB AND ETC, TOTAL 21 EA. | 500 | NRR | WNG | SM | 5700 | 0.01 | 8.01 | WIP
VTL5272 | 777 BASIC CLOSE 600 | FOUND MANY ANCHOR NUTS DAMAGE ,NEEDED REPLACE, AT BOTH WING T/E RELATED PANEL: 573CL,577DL,661JT AND ETC, TOTAL 28 EA. | 500 | NRR | WNG | SM | 5700 | 0.01 | 11.01 | WIP
VTL5280 | 777-57-860-01-01 | AT LHW I/B FLAP O/B END, FOUND PAINT IRREGULARITY. | 500 | NRR | WNG | SS | 5700 | 0.01 | 4.02 | WIP
VTL5298 | 777-57-952-02-01 | AT RHW I/B FLAP O/B END, FOUND PAINT IRREGULARITY. | 600 | NRR | WNG | SS | 5700 | 0.01 | 4.02 | WIP
VTL5306 | 777-53-908-00-01 | CAB - EMERGENCY LIGHT BASE FOUND CRACKED AT GLY 2R (2EA), GLY 3L/R (4EA), GLY 4L (2EA), LAV F FWD (1EA), LAV K AFT (2EA), OFAR AFT (1EA). | 200 | NRR | CAB | AV | 3351 | 24 | 24 | WIP
VTL5314 | 777-57-910-02-01 | RHW SLATS FROM NO.8 TO NO.14, FOUND THE SKIRT PANEL PAINT IRREGULARITIES | 500 | NRR | WNG | SS | 5743 | 0.01 | 34.02 | WIP | Will change to 30mhr
VTL5322 | 777-33-060-01-CX-01 | FOUND CABIN L5 DOOR OFAR AREA ONE EMERGENCY PROXIMITY LIGHT ASSY DAMAGED. | 200 | NRP | CAB | AV | 3351 | 2 | 2 | OPEN
VTL5330 | 777-51-000-01-CX-01 | NO.2 ENG INLET COWL LIP FOUND EXISTING BLENDING REAPAIR. | 400 | NRR | ENG | AE | 7100 | 2 | 2 | OPEN
VTL5348 | 777-900002-01-1-01 | EMP 311BL CAVITY FOUND DIRTY | 300 | NRP | EMP | CL | 5500 | 4 | 4 | COMP
VTL5355 | 777-25-050-08-CX-R-01 | PEY SEAT TV ARM CONTROL CABLE FOUND BROKEN AT:30H | 200 | NRP | CAB | SS | 25 | 2 | 2 | OPEN
VTL5363 | 777-20-251-10-01 | LHW L/E PANEL 511CB,511EB,511GB,511LB,511MB, FOUND PAINT IRREGULARITY. | 500 | NRR | WNG | SS | 5700 | 0.01 | 20.02 | WIP | Will change to 10mhr
VTL5371 | 777-20-251-20-01 | LHW L/E PANEL 611CB,611EB,611GB,611KB,611MB, FOUND PAINT IRREGULARITY. | 600 | NRR | WNG | SS | 5700 | 0.01 | 20.02 | WIP | Will change to 10mhr
VTL5389 | 777-900001-01-1-01 | APU COMP LOWER AREA AND APU DOOR FOUND DIRTY | 300 | NRP | ENG | CL | 49 | 8 | 8 | WIP
VTL5397 | 777-900001-01-1-01 | PLS APPLY CIC IN APU COMP LOWER AREA AND APU DOOR | 300 | NRP | ENG | AE | 49 | 8 | 8 | OPEN
VTL5405 | 777-53-904-00-01 | CAB DR R1 LOWER CEILING PNL LATCH FITTING FND MISSING 1EA | 200 | NRR | CAB | AI | 25 | 1 | 1 | WIP
VTL5413 | 777-53-904-00-01 | CABIN G2R GLY SINK DRAIN SEALANT FOUND DETACH | 200 | NRR | CAB | AI | 2530 | 2 | 2 | COMP
VTL5421 | 777-53-904-00-01 | CABIN G2R GLY WORK DECK EDGE SEALANT FOUND DETACH | 200 | NRR | CAB | AI | 2530 | 2 | 2 | COMP
VTL5439 | 777-53-904-00-01 | CAB OFCR LH AND RH HANDSET PNL EDGE TRIM FND DETACH | 200 | NRR | CAB | AI | 2530 | 4 | 4 | COMP
VTL5447 | 777-53-904-00-01 | CAB LAV L FLOOR PAN FND CRACK | 200 | NRR | CAB | AI | 2530 | 4 | 4 | COMP
VTL5454 | 777-57-880-01-01 | AT FLAP SUPPORT FAIRING NO.3, AFT LINKAGE UPPER BEARING, FOUND MIGRATED AND COVER DETACHED. | 500 | NRR | WNG | GW | 5700 | 4 | 4 | COMP
VTL5462 | 777-53-854-00-01 | AFT CGO SLOPE PNL FASTENER FOUND WORN TTL 55EA | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL5470 | 777-53-854-00-01 | AFT CGO CEILING PNL FASTENER FOUND WORN TTL 78EA | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL5488 | 777-53-874-00-01 | BULK CGO STA1886-2062 FLOOR PNL SCREW FOUND WORN TTL 15EA | 100 | NRR | LWR | AI | 2500 | 2 | 2 | OPEN
VTL5496 | 777-53-824-00-01 | FWD CGO BALL MAT SCREW WASHER FOUND WORN AND MISSING TTL 14EA | 100 | NRR | LWR | AI | 2500 | 2 | 2 | WIP
VTL5504 | 777-53-824-00-01 | FWD CGO L/H 7 R/H SLOPE PNL FASTENER FOUND WORN TTL 67EA | 100 | NRR | LWR | AI | 2500 | 3 | 3 | WIP
VTL5512 | 777-53-824-00-01 | FWD CGO CEILING PNL FASTENER FOUND WORN TTL 77EA | 100 | NRR | LWR | AI | 2500 | 3 | 3 | OPEN
VTL5520 | SWC-28583-01-01 | AT RHW, I/B FLAP, I/B ENG UPPER EDGE, FOUND A SEAL WORN. | 600 | NRW | WNG | AE | 5700 | 2 | 2 | OPEN
VTL5538 | 777-57-943-02-01 | AT RHW WINGTIP, FOUND 2 EA BONDING STRAPS DAMAGE. | 600 | NRR | WNG | AV | 5700 | 0.01 | 0.01 | OPEN
VTL5546 | AEO-25501-01 | RH ECS BAY LWR FCSOV V/V ATTACH TO STRUCTURE BONDING JUMPER AGED | 100 | NRM | FUS | AE | 21 | 0.01 | 2.51 | COMP
VTL5553 | 777-53-904-00-01 | CAB S1R-22 CLOSET SIDE GUIDE FND BROKEN | 200 | NRR | CAB | AI | 2530 | 1 | 1 | OPEN
VTL5561 | 777-53-900-00-01 | COCKPIT LH AND RH NO.2 WINDOW PLACARD FND ILLEGIBLE | 200 | NRR | CAB | AI | 11 | 2 | 2 | COMP
VTL5579 | 777-57-948-02-01 | FOUND RHW T/E CAVITY CIC NOT SATISFIED, RE-APPLY REQ'D. | 600 | NRR | WNG | AE | 5105 | 3 | 3 | OPEN
VTL5587 | 777-57-854-01-01 | FOUND LHW T/E CAVITY CIC NOT SATISFIED, REAPPLY REQ'D. | 500 | NRR | WNG | AE | 5105 | 3 | 3 | OPEN
VTL5595 | 777-57-896-02-01 | FOUND RHW L/E CAVITY CIC NOT SATISFIED, RE-APPLY REQ'D. | 600 | NRR | WNG | AE | 5105 | 2 | 2 | OPEN
VTL5603 | 777-57-804-01-01 | FOUND LHW L/E CAVITY CIC NOT SATISFIED, REAPPLY REQ'D. | 500 | NRR | WNG | AE | 5105 | 2 | 2 | OPEN
VTL5611 | 777 BASIC CLOSE 600 | AT NO.3 FLAP AFT SUPPORT FAIRING, FWD EDGE, FOUND PAINT IRREGULARITY. | 500 | NRR | WNG | SS | 5700 | 0.01 | 4.02 | WIP
VTL5629 | 777 BASIC CLOSE 500 | AT NO.3 FLAP FWD SUPPORT FAIRING, CUTOUT, FOUND PAINT IRREGULARITY. | 500 | NRR | WNG | SS | 5700 | 0.01 | 3.02 | WIP
VTL5637 | 777 BASIC CLOSE 600 | AT NO.6 FLAP AFT SUPPORT FAIRING, FWD EDGE, FOUND PAINT IRREGULARITY. | 500 | NRR | WNG | SS | 5700 | 0.01 | 4.02 | WIP
VTL5645 | 777 BASIC CLOSE 600 | AT NO.6 FLAP FWD SUPPORT FAIRING, CUTOUT, FOUND PAINT IRREGULARITY. | 500 | NRR | WNG | SS | 5700 | 0.01 | 3.02 | WIP
VTL5652 | 777 BASIC CLOSE 600 | RHW L/E LWR WING PNL - 611GB, EXT FOUND DISBOND, TOTAL: 2 EA. | 600 | NRR | WNG | SS | 5700 | 0.01 | 26.53 | WIP
VTL5660 | 777 BASIC CLOSE 600 | RHW L/E LWR WING PNL - 611CB, EXT FOUND DISBOND, TOTAL: 1 EA. | 600 | NRR | WNG | SS | 5700 | 0.01 | 17.53 | WIP
VTL5678 | 777 BASIC CLOSE 600 | RHW L/E LWR WING PNL - 611JB, EXT FOUND DISBOND, TOTAL: 1 EA. | 600 | NRR | WNG | SS | 5700 | 0.01 | 17.53 | WIP
VTL5686 | 777 BASIC CLOSE 600 | RHW L/E LWR WING PNL - 621MB, EXT FOUND DISBOND, TOTAL: 1 EA. | 600 | NRR | WNG | SS | 5700 | 0.01 | 17.53 | WIP
VTL5694 | 777 BASIC CLOSE 500 | LHW L/E LWR WING PNL - 511GB, EXT FOUND DISBOND, TOTAL: 2 EA. | 500 | NRR | WNG | SS | 5700 | 0.01 | 26.53 | WIP
VTL5702 | 777 BASIC CLOSE 500 | LHW L/E LWR WING PNL - 511FB, EXT FOUND DISBOND, TOTAL: 1 EA. | 500 | NRR | WNG | SS | 5700 | 0.01 | 17.53 | WIP
VTL5710 | 777 BASIC CLOSE 500 | LHW L/E LWR WING PNL - 511JB, EXT FOUND DISBOND, TOTAL: 1 EA. | 500 | NRR | WNG | SS | 5700 | 0.01 | 17.53 | WIP
VTL5728 | 777-C252430-01-07-01 | PEY SEAT RECLINE BUTTON FND DAMAGED AT:33D | 200 | NRR | CAB | SS | 25 | 1 | 1 | OPEN
VTL5736 | 777-53-858-00-01 | AFT CGO COMP'T BALL MAT AREA RED LOCK FOUND PAINT PEELED.TTL36EA | 100 | NRR | LWR | PT | 5121 | 18 | 18 | OPEN
VTL5744 | 777-53-820-00-01 | FWD CGO COMP'T BALL MAT AREA RED LOCK FOUND RED PAINT PEELED.TTL:36EA | 100 | NRR | LWR | PT | 5121 | 18 | 18 | OPEN
VTL5751 | 777-53-858-00-01 | AFT CGO STA1434-1886 SIDE WALL PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5769 | 777-53-858-00-01 | AFT CGO STA1434-1886 CEILING PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5777 | 777-53-870-00-01 | BULK CGO STA1889-2062 SIDE WALL & CEILING PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5785 | 777-53-820-00-01 | FWD CGO STA409-998 CEILING PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5793 | 777-53-820-00-01 | FWD CGO STA409-998 SIDE WALL PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5801 | 777-900003-01-1-01 | FOUND CABIN L3 DOOR AFTER EXIT SIGN LIGHT LENS DAMAGED. | 200 | NRP | CAB | AV | 3351 | 1 | 1 | OPEN
VTL5819 | 777-53-854-00-01 | FWD CGO STA445 L/H BILGE AREA 1EA STAND OFF FOUND BROKEN. | 100 | NRR | LWR | SM | 5140 | 0.01 | 4.51 | WIP
VTL5827 | 777-52-827-01-01 | M/D ALL PAX DR CUTOUT AND DR FRAME CUTOUT SOME PLASTIC COVER PNLS FND PAINT CHIPPED | 200 | NRR | CAB | PT | 25 | 10 | 10 | OPEN
VTL5835 | 777-53-910-00-01 | CAB DR 1 FLOOR MAT TRANSFER TRIM FND DEFORMED | 200 | NRR | CAB | AI | 25 | 2 | 2 | OPEN
VTL5843 | 777-53-910-00-01 | CAB DR 2 FLOOR MAT TRANSFER TRIM FND DEFORMED | 200 | NRR | CAB | AI | 25 | 4 | 4 | OPEN
VTL5850 | 777-53-910-00-01 | CAB DR 4 FLOOR MAT TRANSFER TRIM FND DEFORMED | 200 | NRR | CAB | AI | 25 | 4 | 4 | OPEN
VTL5868 | 777-53-910-00-01 | CAB DR 5 FLOOR MAT TRANSFER TRIM FND DEFORMED | 200 | NRR | CAB | AI | 25 | 2 | 2 | OPEN
VTL5876 | 777-53-910-00-01 | CAB DR R2 FWD PARTITION AFT FACE WALLPAPER SURFACE FND SCRATCH | 200 | NRR | CAB | AI | 25 | 2 | 2 | WIP
VTL5884 | 777-53-820-00-01 | FWD CGO STA409-998 SLOPE PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5892 | 777-53-858-00-01 | AFT CGO STA1434-1886 SLOPE PNL FIRE PROOF TAPE FOUND TORN | 100 | NRR | LWR | AI | 2500 | 0.01 | 0.01 | OPEN
VTL5900 | TA28000201 | PERFORM THE FUEL LEAK CHECK AT LH MAIN TANK ACCESS DOORS. | 500 | NRR | F/T | AE | 2800 | 1 | 1 | OPEN
VTL5918 | TA28000201 | PERFORM THE FUEL LEAK CHECK AT RH MAIN TANK ACCESS DOORS. | 600 | NRR | F/T | AE | 2800 | 1 | 1 | OPEN
VTL5926 | TA28000201 | PERFORM THE FUEL LEAK CHECK AT CENTER TANK ACCESS DOORS. | 100 | NRR | F/T | AE | 2800 | 1 | 1 | OPEN

## Detail_CWS
sheet | item_no | work_desc | proj_id | job_jsn | est_eff_mhr | dock_trade
1C | 1 | TOW THE A/C FROM 10 BAY O/S TO 9BAY HANGAR | VT | L001 | 5 | AE
1C | 1 | REMOVE BODYFAIRING 191SL &192SR | VT | L004 | 0.01 | AE
1C | 2 | AIR MOD SIMULATION PREPARATION | VT | L004 | 0.01 | AV
1C | 3 | LIFT THE AIRCRAFT WITH JACK | VT | L004 | 0.01 | AE
1C | 4 | PLS CARRY OUT WOW LOAD SENSOR CALIBRATION | VT | L004 | 0.01 | AV
2C | 5 | LOWER THE AIRCRAFT OFF OF THE JACK | VT | L004 | 0.01 | AE
2C | 6 | REINSTALL THE BODYFAIRING191SL&192SR | VT | L004 | 0.01 | AE
2C | 7 | AIR MODE SIMULATION RESTORATION | VT | L004 | 0.01 | AV
1C | 1 | REMOVE BPCU | VT | L007 | 2 | AV
1C | 2 | INSTALL BPCU | VT | L007 | 2 | AV
2C | 3 | REMOVE BPCU | VT | L007 | 2 | AV
2C | 4 | INSTALL BPCU | VT | L007 | 2 | AV
3C | 5 | REMOVE BPCU | VT | L007 | 1 | AV
3C | 6 | INSTALL BPCU | VT | L007 | 1 | AV
3C | 7 | PERFORM BPCU INSTALLATION TEST | VT | L007 | 1 | AV
1C | 1 | REPLACE ROTARY ACTUATORS | VT | L025 | 12 | AI
1C | 2 | ADJUST DOOR LIFT MECHANISM | VT | L025 | 4 | AI
1C | 3 | PERFORM INSTALLATION TEST | VT | L025 | 1 | AI
1C | 1 | DISCONNECT ELECT CONNECTOR | VT | L027 | 0.5 | AV
1C | 2 | REPLACE LIFT ACTUATOR | VT | L027 | 6 | AI
1C | 3 | PERFORM BONDING TEST | VT | L027 | 0.5 | AV
1C | 4 | CONNECT ELECT CONNECTOR | VT | L027 | 0.5 | AV
2C | 5 | PERFORM INSTALLATION TEST | VT | L027 | 1 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L028 | 0.2 | AI
2C | 2 | PERFORM TROUBLE SHOOTING | VT | L028 | 2 | AV
2C | 3 | REPLACE THE MODE CONTROL PANEL (MCP) M22016 | VT | L028 | 2 | AV
2C | 4 | PERFORM MCP INSTALLATION TEST | VT | L028 | 1 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L032 | 0.01 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L034 | 0.2 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L039 | 0.2 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L041 | 0.2 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L042 | 0.2 | AE
2C | 2 | REMOVE THE MEC FLOOR PNL | VT | L042 | 0.5 | AI
2C | 3 | REMOVE THE HI-LOCK ATT TO HINGLE ASSY | VT | L042 | 1 | SM
2C | 4 | REPLACE THE HINGLE ASSY | VT | L042 | 6 | AE
2C | 5 | INSTALL THE HI-LOCK TO HINGLE ASSY | VT | L042 | 1 | SM
3C | 6 | C/O HINGLE ASSY INSTALLATION TEST | VT | L042 | 0.5 | AE
3C | 7 | INSTALL THE THE MEC FLOOR PNL | VT | L042 | 0.5 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L045 | 0.2 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L046 | 0.2 | AE
2C | 2 | REMOVE DMS ELEC CONNECTOR REF | VT | L046 | 1 | AV
2C | 3 | PERFORM DMS INSP REF | VT | L046 | 2 | AE
2C | 4 | INSTALL DMS ELEC CONNECTOR REF | VT | L046 | 1 | AV
2C | 5 | PERFORM DMS MAT TEST REF | VT | L046 | 1 | AV
3C | 6 | PERFORM IDLE LEAK CHK REF | VT | L046 | 1 | AE
3C | 7 | PERFORM ENG OIL SYSTEM LUBE AND SCAVENGE SCREEN AND MAG PLUG INSP REF | VT | L046 | 5 | AE
3C | 8 | PERFORM IDLE LEAK CHK IN INLET SCREW AREA REF | VT | L046 | 1 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L047 | 0.2 | AE
2C | 2 | REMOVE DMS ELEC CONNECTOR REF | VT | L047 | 1 | AV
2C | 3 | PERFORM DMS INSP REF | VT | L047 | 2 | AE
2C | 4 | INSTALL DMS ELEC CONNECTOR REF | VT | L047 | 1 | AV
2C | 5 | PERFORM DMS MAT TEST REF | VT | L047 | 1 | AV
3C | 6 | PERFORM IDLE LEAK CHK REF | VT | L047 | 1 | AE
3C | 7 | PERFORM ENG OIL SYSTEM LUBE AND SCAVENGE SCREEN AND MAG PLUG INSP REF | VT | L047 | 5 | AE
3C | 8 | PERFORM IDLE LEAK CHK IN INLET SCREW AREA REF | VT | L047 | 1 | AE
1C | 1 | CONTINUE PART 1, CLEAR SADD RAISED AGAINST THIS AEO PART 1. | VT | L048 | 0.01 | AI
1C | 2 | PLS MAKE LOG BOOK ENTRY. | VT | L048 | 0.2 | AI
1C | 1 | DISCONNECT ELECT CONNECTOR | VT | L049 | 0.5 | AV
1C | 2 | REPLACE LIFT ACTUATOR | VT | L049 | 6 | AI
1C | 3 | PERFORM BONDING TEST | VT | L049 | 0.5 | AV
1C | 4 | CONNECT ELECT CONNECTOR | VT | L049 | 0.5 | AV
2C | 5 | PERFORM INSTALLATION TEST | VT | L049 | 1 | AI
1C | 1 | REPLACE ROTARY ACTUATORS | VT | L050 | 8 | AI
1C | 2 | ADJUST DOOR LIFT MECHANISM | VT | L050 | 4 | AI
1C | 3 | PERFORM INSTALLATION TEST | VT | L050 | 1 | AI
1C | 1 | CONTINUE AS PER AEO-27666 PART 2, AND AEO-27669 PART 2 , CLEAR SADD RAISED AGAINST THIS AEO PART 1. | VT | L051 | 0.01 | AI
1C | 2 | PLS MAKE LOG BOOK ENTRY. | VT | L051 | 0.2 | AI
1C | 1 | PERFORM THE L/E SLAT - DEACTIVATION. | VT | L052 | 2 | AE
1C | 2 | PERFORM THE L/E SLAT - REACTIVATION. | VT | L052 | 2 | AE
1C | 1 | DISCONNECT THE ELECTRICAL CONNECTOR FROM THE SLAT MOTOR ASSEMBLY | VT | L053 | 1 | AV
1C | 2 | RE-CONNECT THE ELECTRICAL CONNECTOR FROM THE SLAT MOTOR ASSEMBLY | VT | L053 | 1 | AV
1C | 3 | SLAT ELECTRIC MOTOR REMOVE FOR MANUAL OPERATION | VT | L053 | 2 | AE
1C | 4 | L/E SLAT SYS MANUAL OPERATE TO RETRACTED POSITION. | VT | L053 | 4 | AE
2C | 5 | L/E SLAT SYS MANUAL OPERATE TO EXTENDED POSITION. | VT | L053 | 4 | AE
2C | 6 | SLAT ELECTRIC MOTOR INSTALL AFT MANUAL OPERATION | VT | L053 | 2 | AE
2C | 7 | PERFORM SLAT SYSTEM SECONDARY CONTROL TEST | VT | L053 | 2 | AE
1C | 1 | CONTINUE FERRY FLIGHT OPERATIONS ARE ALLOWED.THE CENTER TANK MUST NOT BE REFUELED DURING THIS PERIOD. | VT | L054 | 0.01 | AV
1C | 2 | PLS MAKE LOG BOOK ENTRY. | VT | L054 | 0.2 | AV
2C | 3 | PERFORM TASK 28-AWL-01 | VT | L054 | 4 | AV
2C | 4 | PERFORM TASK 28-AWL-01 | VT | L054 | 4 | AV
1C | 1 | PERFORM THE T/E FLAP - DEACTIVATION. | VT | L055 | 2 | AE
1C | 2 | PERFORM THE T/E FLAP - REACTIVATION. | VT | L055 | 2 | AE
1C | 1 | REMOVE THE OVEN ELEC PLUG | VT | L056 | 0.2 | AV
1C | 2 | REMOVE THE OVEN | VT | L056 | 0.5 | AI
1C | 3 | INSTALL THE OVEN | VT | L056 | 0.5 | AI
1C | 4 | INSTALL THE OVEN ELEC PLUG | VT | L056 | 0.2 | AV
2C | 5 | PERFORM TEST WITH THE OVEN | VT | L056 | 0.5 | AV
1C | 1 | REMOVE FB2 SEAT PARTITION SIDE CONSOLE AREA ATTACH PARTS | VT | L057 | 3.5 | AI
1C | 2 | CAB FB2 SEAT PARTITION SIDE CONSOLE AREA TEDLAR REPLACE | VT | L057 | 40 | SS
1C | 3 | CAB FB2 SEAT PARTITION SIDE CONSOLE AREA ATTACH PARTS | VT | L057 | 4 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L058 | 0.2 | AI
2C | 2 | PERFORM OFCR POWER SUPPLY BATTERY PACK CAPACITY CHECK | VT | L058 | 1 | AV
2C | 3 | PERFORM OFAR POWER SUPPLY BATTERY PACK CAPACITY CHECK | VT | L058 | 1 | AV
1C | 1 | REMOVE #1 DOOR S1 STOWAGE FWD AND OFCR FWD B/HEAD PANEL BUMPER AND ATTACH PARTS | VT | L059 | 2 | AI
1C | 2 | #1 DOOR S1 STOWAGE FWD AND OFCR FWD B/HEAD PANEL TEDLAR REPLACE | VT | L059 | 22 | SS
1C | 3 | REMOVE #1 DOOR S1 STOWAGE FWD AND OFCR FWD B/HEAD PANEL PROXIMITY LIGHT | VT | L059 | 1 | AV
1C | 4 | REINSTALL #1 DOOR S1 STOWAGE FWD AND OFCR FWD B/HEAD PANEL BUMPER AND ATTACH PARTS | VT | L059 | 2 | AI
2C | 5 | REINSTALL #1 DOOR S1 STOWAGE FWD AND OFCR FWD B/HEAD PANEL PROXIMITY LIGHT | VT | L059 | 2 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L060 | 0.2 | AV
2C | 2 | PERFORM IFE SYSTEM WIRING INSPECTION | VT | L060 | 6 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L061 | 0.2 | AE
2C | 2 | PLS REMOVE IDG ELECTRICAL CONNECTOR REF | VT | L061 | 2 | AV
2C | 3 | PLS REMOVE IDG REF | VT | L061 | 8 | AE
2C | 4 | INSTALL IDG ELECTRICAL CONNECTOR REF | VT | L061 | 3 | AV
2C | 5 | INSTALL IDG REF | VT | L061 | 12 | AE
3C | 6 | PERFORM DRY MOTOR LEAK CHK REF | VT | L061 | 1 | AE
3C | 7 | PERFORM IDLE LEAK CHK REF | VT | L061 | 1 | AE
3C | 8 | PERFORM PART POWER LEAK CHK REF | VT | L061 | 1 | AE
3C | 9 | PERFORM IDG OPERATIONAL TEST REF | VT | L061 | 1 | AE
4C | 10 | PERFORM IDG DISCONNECT CHK REF | VT | L061 | 4 | AE
1C | 1 | CAB REMOVE #2 DOOR G2 GLY L/R AISLE S/W ARED ATTACH PARTS | VT | L062 | 2 | AI
1C | 2 | CAB #2 DOOR G2 GLY L/R AISLE S/W ARED TADLAR REPLACE | VT | L062 | 22 | SS
1C | 3 | CAB REMOVE #2 DOOR G2 GLY L/R AISLE S/W ARED PANEL PROXIMITY LIGHT | VT | L062 | 1 | AV
1C | 4 | CAB REINSTALL #2 DOOR G2 GLY L/R AISLE S/W ARED ATTACH PARTS | VT | L062 | 2 | AI
2C | 5 | CAB #2 DOOR G2 GLY L/R AISLE S/W ARED PANEL PROXIMITY LIGHT | VT | L062 | 2 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L063 | 0.2 | AV
2C | 2 | REPLACE LAPTOP IN THE MEC | VT | L063 | 1 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L065 | 0.2 | AI
2C | 2 | REMOVE THE SLIDE | VT | L065 | 1.5 | AI
2C | 3 | INSTALL THE SLIDE | VT | L065 | 2 | AI
2C | 4 | PERFORM IPI PROCEDURE | VT | L065 | 0.2 | AI
1C | 1 | REMOVE G8 L/H AND R/H S8-01 COMPT DOOR BUMPER AND ATTACH PART | VT | L066 | 1.5 | AI
1C | 2 | G8 GLY LHS AND RH S8-01 DOOR TEDLAR REPLACE | VT | L066 | 12 | SS
1C | 3 | REINSTALL G8 L/H AND R/H S8-01 COMPT DOOR BUMPER AND ATTACH PART | VT | L066 | 2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L067 | 0.2 | AI
2C | 2 | REMOVE THE SLIDE | VT | L067 | 1.5 | AI
2C | 3 | INSTALL THE SLIDE | VT | L067 | 2 | AI
2C | 4 | PERFORM IPI PROCEDURE | VT | L067 | 0.2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L068 | 0.2 | AI
2C | 2 | DISCONNECT THE ELEC CONNECTOR OF THE SLIDE | VT | L068 | 0.2 | AV
2C | 3 | REMOVE THE SLIDE | VT | L068 | 2.5 | AI
2C | 4 | CONNECT THE ELEC CONNECTOR OF THE SLIDE | VT | L068 | 0.2 | AV
2C | 5 | INSTALL THE SLIDE | VT | L068 | 3 | AI
3C | 6 | PERFORM IPI PROCEDURE | VT | L068 | 0.2 | AI
3C | 7 | PERFORM OFF-WIND ESCAPE SLIDE LIGHT TEST | VT | L068 | 0.5 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L069 | 0.2 | AV
2C | 2 | REPLACE DOOR L3 EPAS BATTERY PACK | VT | L069 | 2 | AV
2C | 3 | PERFORM IPI REQUIREMENT | VT | L069 | 0.2 | AV
2C | 4 | PERFORM EPAS BATTERY PACK OPERATIONAL TEST | VT | L069 | 1 | AV
1C | 1 | CAB REMOVE #1 DOOR OFCR DOOR AISLE S/W ATTACH PARTS | VT | L070 | 2 | AI
1C | 2 | CAB #1 DOOR OFCR DOOR AISLE S/W TEDLAR REPLACE | VT | L070 | 11 | SS
1C | 3 | CAB REINSTALL #1 DOOR OFCR DOOR AISLE S/W ATTACH PARTS | VT | L070 | 2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L071 | 0.2 | AV
2C | 2 | REPLACE DOOR R3 EPAS BATTERY PACK | VT | L071 | 2 | AV
2C | 3 | PERFORM IPI REQUIREMENT | VT | L071 | 0.2 | AV
2C | 4 | PERFORM EPAS BATTERY PACK OPERATIONAL TEST | VT | L071 | 1 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L072 | 0.2 | AV
2C | 2 | REPLACE DOOR L3 BACKUP BATTERY PACK | VT | L072 | 2 | AV
2C | 3 | PERFORM IPI REQUIREMENT | VT | L072 | 0.2 | AV
2C | 4 | C/O EPAS BACKUP BATTERY PACK OPERATIONAL TEST | VT | L072 | 1 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L073 | 0.2 | AV
2C | 2 | REPLACE DOOR R3 BACKUP BATTERY PACK | VT | L073 | 2 | AV
2C | 3 | PERFORM IPI REQUIREMENT | VT | L073 | 0.2 | AV
2C | 4 | C/O EPAS BACKUP BATTERY PACK OPERATIONAL TEST | VT | L073 | 1 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L074 | 0.2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L075 | 0.2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L076 | 0.2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L077 | 0.2 | AV
2C | 2 | PERFORM NETWORK FILE SERVER SECURITY LOGS DOWNLOAD | VT | L077 | 2 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L078 | 0.2 | AI
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L079 | 0.2 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L080 | 0.2 | AI
2C | 2 | DISCONNECT ELECT CONNECTOR | VT | L080 | 0.5 | AV
2C | 3 | INSTALL ELECT CONNECTOR AND RELATE WIRING | VT | L080 | 0.5 | AV
2C | 4 | REPLACE PDU | VT | L080 | 2 | AI
2C | 5 | PERFORM BONDING TEST | VT | L080 | 0.5 | AV
3C | 6 | PERFORM INSTALLATION TEST | VT | L080 | 0.5 | AV
1C | 1 | CONTINUE RH CTR DOG HOSE FWD FWD OF LAV K. UNSERVICEABLE OXY BOTTLES MARKED U/S. | VT | L082 | 0.01 | AV
1C | 2 | PLS MAKE LOG BOOK ENTRY. | VT | L082 | 0.2 | AV
2C | 3 | REPLACE PORTABLE OXY CYLINDER INSIDE STOWAGE S2L AFT OF DOOR 2L | VT | L082 | 1 | AV
2C | 4 | REPLACE PORTABLE OXY CYLINDER INSIDE STOWAGE S2R AFT OF DOOR 2R | VT | L082 | 1 | AV
2C | 5 | REPLACE PORTABLE OXY CYLINDER INSIDE LH CTR DOGHOUSE FWD OF LAV E (LWR) | VT | L082 | 1 | AV
2C | 6 | REPLACE PORTABLE OXY CYLINDER INSIDE RH CTR DOGHOUSE FWD OF LAV F (UPPER) | VT | L082 | 1 | AV
3C | 7 | REPLACE PORTABLE OXY CYLINDER INSIDE RH CTR DOGHOUSE FWD OF LAV F (LWR) | VT | L082 | 1 | AV
3C | 8 | REPLACE PORTABLE OXY CYLINDER INSIDE LH CTR DOGHOUSE FWD OF GALLEY G4 (LWR) | VT | L082 | 1 | AV
3C | 9 | REPLACE PORTABLE OXY CYLINDER INSIDE RH CTR DOGHOUSE FWD OF GALLEY G4 (UPPER) | VT | L082 | 1 | AV
3C | 10 | REPLACE PORTABLE OXY CYLINDER INSIDE LH CTR DOGHOUSE FWD OF OFAR (MID) | VT | L082 | 1 | AV
4C | 11 | REPLACE PORTABLE OXY CYLINDER INSIDE RH CTR DOGHOUSE FWD OF LAV K (UPPER) | VT | L082 | 1 | AV
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L085 | 0.2 | AE
1C | 1 | PLS MAKE LOG BOOK ENTRY. | VT | L088 | 0.2 | AI
1C | 1 | C/O DENT AREA REPAIR | VT | L099 | 0.1 | AI
1C | 2 | C/O REPAIR AREA TOUCH UP PAINT | VT | L099 | 0.5 | PT
1C | 1 | REMOVE COMPARTMENT DOOR LOWER TRIM | VT | L105 | 2 | AI
1C | 2 | TRANSFER FASTENER HOLE AND CUTOUT TO NEW PART | VT | L105 | 2 | SM
1C | 3 | INSTALL COMPARTMENT DOOR LOWER TRIM | VT | L105 | 1.5 | AI
1C | 1 | REMOVE CABIN ALL AISLE FLOOR CARPETS | VT | L108 | 40 | CL
1C | 2 | FABRICATE CABIN ALL AISLE FLOOR CARPETS TTL47EA | VT | L108 | 60 | SS
1C | 3 | INSTALL CABIN ALL AISLE FLOOR CARPETS | VT | L108 | 88 | CL
1C | 4 | REMOVE SEAT TRACK COVER | VT | L108 | 8 | SS
2C | 5 | INSTALL SEAT TRACK COVER | VT | L108 | 12 | SS
1C | 1 | REMOVE UNDER SEAT FLOOR CARPETS | VT | L110 | 16 | CL
1C | 2 | FABRICATE UNDER SEAT FLOOR CARPETS | VT | L110 | 46.5 | SS
1C | 3 | INSTALL UNDER SEAT FLOOR CARPETS | VT | L110 | 45 | CL
1C | 1 | REMOVE 15G,20G VIDEO MONITOR CABLE ASSEMBLY | VT | L115 | 2 | AV
1C | 2 | REPLACE 15G,20G TOP HINGE ASSY SPRING | VT | L115 | 2 | AI
1C | 3 | PERFORM 7EA VIDEO MONITOR LATCH AND LOCK ASSEMBLY ADJUSTMENT | VT | L115 | 17.5 | AI
1C | 4 | INSTALL 15G,20G VIDEO MONITOR CABLE ASSEMBLY | VT | L115 | 2 | AV
1C | 1 | REMOVE DFDR | VT | L116 | 1 | AV
1C | 2 | INSTALL DFDR | VT | L116 | 1 | AV
1C | 3 | PERFORM DFDR INSTALLATION TEST | VT | L116 | 1 | AV
1C | 4 | REMOVE ULB | VT | L116 | 1 | AV
2C | 5 | INSTALL ULB | VT | L116 | 0.5 | AV
1C | 1 | REPLACE LAMP OF LOGO LIGHT | VT | L152 | 2 | AV
1C | 2 | REPLACE R/H AFT LOGO LIGHT ASSEMBLY | VT | L152 | 4 | AV
1C | 3 | TEST R/H AFT LOGO LIGHT ASSEMBLY | VT | L152 | 0.5 | AV
1C | 1 | DISCONNECT CONNECTOR OF MAIN BATTERY | VT | L153 | 1 | AV
1C | 2 | DISCONNECT CONNECTOR OF APU BATTERY | VT | L153 | 1 | AV
1C | 3 | RECONNECT CONNECTOR OF MAIN BATTERY | VT | L153 | 1 | AV
1C | 4 | RECONNECT CONNECTOR OF APU BATTERY | VT | L153 | 1 | AV
2C | 5 | PERFORM MAIN BATTERY RECONNECTION TEST | VT | L153 | 0.5 | AV
2C | 6 | PERFORM APU BATTERY RECONNECTION TEST | VT | L153 | 0.5 | AV
1C | 1 | REMOVE LOWER AFT VHF ANTENNA | VT | L154 | 0.01 | AV
1C | 2 | INSTALL LOWER AFT VHF ANTENNA | VT | L154 | 0.01 | AV
1C | 3 | PERFORM INSTALLATION TEST OF LOWER AFT VHF ANTENNA | VT | L154 | 0.01 | AV
1C | 1 | REMOVE COCKPIT FLOOR CARPET | VT | L160 | 2 | CL
1C | 2 | FABICATE COCKPIT FLOOR CARPET | VT | L160 | 10 | SS
1C | 3 | INSTALL COCKPIT FLOOR CARPET | VT | L160 | 6 | CL
2C | 4 | CLEAN COCKPIT REMOVED FLOOR CARPETS AREA FLOOR PNL SURFACE FND DIRTY AND RESIDUAL DOUBLE TAPE | VT | L160 | 6 | CL
1C | 1 | DISCONNECT CONNECTOR OF LOWER ANTI-COLLISION LIGHT | VT | L161 | 1 | AV
1C | 2 | RECONNECT CONNECTOR OF LOWER ANTI-COLLISION LIGHT | VT | L161 | 1 | AV
1C | 3 | PERFORM TEST OF LOWER ANTI-COLLISION LIGHT | VT | L161 | 0.5 | AV
1C | 1 | PERFORM TROUBLE SHOOTING | VT | L162 | 1 | AV
1C | 2 | DEFLATE THE TIRE | VT | L162 | 1 | AE
1C | 3 | REPLACE THE TIRE PRESSURE SENSOR | VT | L162 | 2 | AV
1C | 4 | PERFORM LANDING GEAR TIRE SERVICING | VT | L162 | 2 | AE
2C | 5 | PERFORM THE TIRE PRESSURE SENSOR/FILL VALVE INSTALLATION TEST | VT | L162 | 1 | AV
1C | 1 | PERFORM TROUBLE SHOOTING | VT | L170 | 1 | AV
1C | 2 | DEFLATE THE TIRE | VT | L170 | 1 | AE
1C | 3 | REPLACE THE TIRE PRESSURE SENSOR | VT | L170 | 2 | AV
1C | 4 | PERFORM LANDING GEAR TIRE SERVICING | VT | L170 | 2 | AE
2C | 5 | PERFORM THE TIRE PRESSURE SENSOR/FILL VALVE INSTALLATION TEST | VT | L170 | 1 | AV
1C | 1 | REMOVE THE LIP SKIN CORROSION | VT | L171 | 36 | SM
1C | 2 | PTOTECT THE REWORK AREA | VT | L171 | 4 | SM
1C | 3 | NDT THICKNESS CHK | VT | L171 | 30 | NT
1C | 4 | NDT CRACK CHK | VT | L171 | 4 | NT
2C | 5 | CLEAN ENG INLET COWL LIP SKIN | VT | L171 | 5 | CL
1C | 1 | REMOVE THE LIP SKIN CORROSION | VT | L172 | 40 | SM
1C | 2 | PTOTECT THE REWORK AREA | VT | L172 | 4 | SM
1C | 3 | NDT THICKNESS CHK | VT | L172 | 100 | NT
1C | 4 | NDT CRACK CHK | VT | L172 | 24 | NT
1C | 1 | REMOVE CENTER RA RECEIVER AND TRANSMIT ANTENNA | VT | L192 | 2 | AV
1C | 2 | INSTALL CENTER RA RECEIVER AND TRANSMIT ANTENNA | VT | L192 | 4 | AV
1C | 3 | PERFORM INSTALLATION TEST OF CENTER RA RECEIVER AND TRANSMIT ANTENNA | VT | L192 | 1 | AV
1C | 1 | REMOVE MARKER BEACON ANTENNA | VT | L193 | 1 | AV
1C | 2 | INSTALL E MARKER BEACON ANTENNA | VT | L193 | 2 | AV
1C | 3 | PERFORM INSTALLATION TEST OF MARKER BEACON ANTENNA | VT | L193 | 1 | AV
1C | 1 | REMOVE DME ANTENNA | VT | L194 | 2 | AV
1C | 2 | INSTALL DME ANTENNA | VT | L194 | 4 | AV
1C | 3 | PERFORM INSTALLATION TEST OF DME ANTENNA | VT | L194 | 1 | AV
1C | 1 | REMOVE LOWER ATC ANTENNA | VT | L195 | 1 | AV
1C | 2 | INSTALL LOWER ATC ANTENNA | VT | L195 | 2 | AV
2C | 3 | PERFORM INSTALLATION TEST OF LOWER ATC ANTENNA | VT | L195 | 1 | AV
1C | 1 | REMOVE LOWER TCAS ANTENNA | VT | L196 | 1 | AV
1C | 2 | INSTALL LOWER TCAS ANTENNA | VT | L196 | 2 | AV
1C | 3 | PERFORM INSTALLATION TEST OF LOWER TCAS ANTENNA | VT | L196 | 1 | AV
1C | 1 | C/O CRACK AREA REPAIR | VT | L197 | 0.1 | AI
1C | 2 | C/O REPAIR AREA TOUCH UP PAINT | VT | L197 | 0.5 | PT
1C | 1 | C/O CRACK AREA REPAIR | VT | L198 | 0.1 | AI
1C | 2 | C/O REPAIR AREA TOUCH UP PAINT | VT | L198 | 0.5 | PT
1C | 1 | REMOVE THE MISSING LATCH | VT | L200 | 2 | SM
1C | 2 | TRANSFER HOLE NEW LATCH | VT | L200 | 1 | SM
1C | 3 | INSTALL THE NEW LATCH | VT | L200 | 3 | SM
1C | 4 | TOUCH UP PAINT | VT | L200 | 0.5 | PT
1C | 1 | REMOVE THE MISSING LATCH | VT | L202 | 2 | SM
1C | 2 | TRANSFER HOLE NEW LATCH | VT | L202 | 1 | SM
1C | 3 | INSTALL THE NEW LATCH | VT | L202 | 3 | SM
1C | 4 | TOUCH UP PAINT | VT | L202 | 0.5 | PT
1C | 1 | REPLACED DAMAGE ANCHOR NUT | VT | L204 | 2 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L204 | 1 | PT
1C | 1 | DISCONNECT HF ANTENNA FEEDLINE | VT | L206 | 2 | AV
1C | 2 | REMOVE PNL 321E | VT | L206 | 0.01 | AE
1C | 3 | APPLY ANTI-STATIC COATING TO SURFACE | VT | L206 | 30 | PT
1C | 4 | C/O RESISTANCE CHECK | VT | L206 | 2 | AV
2C | 5 | RESTORE THE ORIGINAL FINISH COATING | VT | L206 | 14 | PT
2C | 6 | RECONNECT THE HF ANTENNA FEEDLINE CONNECTOR | VT | L206 | 2 | AV
2C | 7 | RE-INSTALL THE 321E | VT | L206 | 0.01 | AE
2C | 8 | C/O HF SYSTEM TEST | VT | L206 | 1 | AV
3C | 9 | DISCONNECT HF ANTENNA FEEDLINE | VT | L206 | 2 | AV
1C | 1 | REPLACED DAMAGE STAND OFFS | VT | L207 | 2 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L207 | 1 | PT
1C | 1 | REMOVE CORROSION | VT | L208 | 2 | SM
1C | 2 | PTOTECT THE REWORK AREA | VT | L208 | 2 | SM
1C | 3 | NDT THICKNESS CHK | VT | L208 | 2 | NT
1C | 4 | NDT CRACK CHK | VT | L208 | 1 | NT
2C | 5 | PLEASE CARY OUT REPAIR INSTRUCTIONS AS PER RS-34713 REV 00. | VT | L208 | 0.01 | AI
1C | 1 | REMOVE CORROSION LATCH | VT | L209 | 2 | SM
1C | 2 | INSTALL NEW LATCHS | VT | L209 | 3 | SM
1C | 3 | TOUCH UP TOP COAT | VT | L209 | 1 | PT
1C | 1 | REMOVE THE BROKEN HINGE | VT | L210 | 2 | SM
1C | 2 | TRANSFER HOLE NEW HINGE | VT | L210 | 2 | SM
1C | 3 | INSTALL THE NEW HINGE | VT | L210 | 3 | SM
1C | 4 | TOUCH UP PAINT | VT | L210 | 0.5 | PT
1C | 1 | REPLACE THE BONDING JUMPER | VT | L234 | 3 | AE
1C | 2 | PLS CARRY OUT BONDING JUMPER RESISTANCE TEST | VT | L234 | 0.5 | AV
1C | 1 | REPLACE THE BONDING JUMPER | VT | L235 | 3 | AE
1C | 2 | PLS CARRY OUT BONDING JUMPER RESISTANCE TEST | VT | L235 | 0.5 | AV
1C | 1 | REMOVE THE HUBCAP | VT | L236 | 0.5 | AE
1C | 2 | DISCONNECT THE ELECTRICAL CONNECTOR | VT | L236 | 0.2 | AV
1C | 3 | REMOVE THE WHEEL AND TIRE ASSEMBLY | VT | L236 | 2 | AE
1C | 4 | INSTALL THE WHEEL AND TIRE ASSEMBLY | VT | L236 | 2 | AE
2C | 5 | INSTALL THE ELECTRICAL CONNECTOR TO NEW WHEEL TIRE ASSY | VT | L236 | 0.3 | AV
2C | 6 | INSTALL THE HUBCAP | VT | L236 | 0.5 | AE
2C | 7 | PLS C/O LG TIRE SERVICING | VT | L236 | 1 | AE
2C | 8 | C/O WHEEL TIRE ASSY INSTALLATION TEST | VT | L236 | 0.5 | AV
3C | 9 | PERFORM IPI TASK | VT | L236 | 0.2 | AE
1C | 1 | REMOVE THE HINGLE FOR SM | VT | L237 | 1 | AE
1C | 2 | PLEASE TRANSFER HOLES FOR NEW HINGLE | VT | L237 | 1 | SM
1C | 3 | REINSTALL THE HINGLE | VT | L237 | 1 | AE
1C | 1 | DISCONNECT FWD CGO DOORWAY CEILING AREA CGO HANDLING CONTROL SWITCH | VT | L239 | 0.5 | AV
1C | 2 | DISCONNECT FWD CGO DOORWAY CEILING AREA CGO DOOR CONTROL SWITCH | VT | L239 | 0.5 | AV
1C | 3 | CONNECT FWD CGO DOORWAY CEILING AREA CGO HANDLING CONTROL SWITCH | VT | L239 | 0.5 | AV
1C | 4 | CONNECT FWD CGO DOORWAY CEILING AREA CGO DOOR CONTROL SWITCH | VT | L239 | 1 | AV
2C | 5 | PERFORM INSTALLATION TEST OF CGO HANDLING CONTROL SWITCH | VT | L239 | 1 | AV
2C | 6 | PERFORM FUNCTIONAL TEST OF INTERNAL CARGO DOOR CONTROL SWITCH | VT | L239 | 0.5 | AV
1C | 1 | DISCONNECT CGO DOORWAY CEILING AREA CGO HANDLING CONTROL SWITCH | VT | L241 | 0.5 | AV
1C | 2 | DISCONNECT CGO DOORWAY CEILING AREA CGO DOOR CONTROL SWITCH | VT | L241 | 0.5 | AV
1C | 3 | CONNECT CGO DOORWAY CEILING AREA CGO HANDLING CONTROL SWITCH | VT | L241 | 0.5 | AV
1C | 4 | CONNECT CGO DOORWAY CEILING AREA CGO DOOR CONTROL SWITCH | VT | L241 | 1 | AV
2C | 5 | PERFORM INSTALLATION TEST OF CGO HANDLING CONTROL SWITCH | VT | L241 | 1 | AV
2C | 6 | PERFORM FUNCTIONAL TEST OF INTERNAL CARGO DOOR CONTROL SWITCH | VT | L241 | 0.5 | AV
1C | 1 | PLEASE CARRY OUT REPAIR INSTRUCTIONS AS PER RS-34691 REV 00. | VT | L252 | 0.01 | AI
2C | 2 | MAKE REPAIR DOUBLER | VT | L252 | 0.01 | SM
2C | 3 | TRANSFER HOLES TO NEW DOUBLER | VT | L252 | 0.01 | SM
2C | 4 | PROTECT NEW DOUBLER | VT | L252 | 0.01 | SM
2C | 5 | APPLY PRIMER TO NEW DOUBLER | VT | L252 | 0.01 | PT
1C | 1 | DISCONNECT ELECT CONNECTOR | VT | L256 | 0.5 | AV
1C | 2 | INSTALL ELECT CONNECTOR AND RELATE WIRING | VT | L256 | 0.5 | AV
1C | 3 | REPLACE PDU | VT | L256 | 2 | AI
1C | 4 | PERFORM BONDING TEST | VT | L256 | 0.5 | AV
2C | 5 | PERFORM INSTALLATION TEST | VT | L256 | 0.5 | AV
1C | 1 | DISCONNECT ELECT CONNECTOR | VT | L258 | 0.5 | AV
1C | 2 | INSTALL ELECT CONNECTOR AND RELATE WIRING | VT | L258 | 0.5 | AV
1C | 3 | REPLACE PDU | VT | L258 | 2 | AI
1C | 4 | PERFORM BONDING TEST | VT | L258 | 0.5 | AV
2C | 5 | PERFORM INSTALLATION TEST | VT | L258 | 0.5 | AV
1C | 1 | REMOVE FB2 PAX SEAT BACKREST ATT LEGREST LINE SCREW 16A | VT | L277 | 1 | GW
1C | 2 | INSTALL FB2 PAX SEAT BACKREST ATT LEG REST LINE SCREW 16A | VT | L277 | 2 | SS
1C | 1 | REPLACED BROKEN ANCHOR NUTS | VT | L283 | 2 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L283 | 1 | PT
1C | 1 | REPLACED BROKEN ANCHOR NUTS | VT | L290 | 2 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L290 | 1 | PT
1C | 1 | C/O DENT AREA REPAIR | VT | L308 | 0.1 | AI
1C | 2 | C/O REPAIR AREA TOUCH UP PAINT | VT | L308 | 0.5 | PT
1C | 1 | C/O DENT AREA REPAIR | VT | L309 | 0.1 | AI
1C | 2 | C/O REPAIR AREA TOUCH UP PAINT | VT | L309 | 0.5 | PT
1C | 1 | C/O DENT AREA REPAIR | VT | L310 | 0.1 | AI
1C | 2 | C/O REPAIR AREA TOUCH UP PAINT | VT | L310 | 0.5 | PT
1C | 1 | REMOVE #5 DOOR K LAV AFT AREA PANEL BUMPER AND ATTACH PARTS | VT | L346 | 1 | AI
1C | 2 | REMOVE #5 DOOR K LAV AFT AREA PANEL PROXIMITY LIGHT PARTS | VT | L346 | 1 | AV
1C | 3 | CAB #5 DOOR K LAV AFT AREA PANEL TADLAR REPLACE | VT | L346 | 12 | SS
1C | 4 | REINSTALL #5 DOOR K LAV AFT AREA PANEL BUMPER AND ATTACH PARTS | VT | L346 | 1 | AI
2C | 5 | REINSTALL #5 DOOR K LAV AFT AREA PANEL PROXIMITY LIGHT PARTS | VT | L346 | 1 | AV
1C | 1 | REMOVE#4 DOOR G4 GLY R/H AISLE S/W ARED PANEL BUMPER AND ATTACH PARTS | VT | L347 | 1 | AI
1C | 2 | REMOVE#4 DOOR G4 GLY R/H AISLE S/W ARED PANEL PROXIMITY LIGHT | VT | L347 | 1 | AV
1C | 3 | #4 DOOR G4 GLY R/H AISLE S/W ARED PANEL TADLAR REPLACE | VT | L347 | 12 | SS
1C | 4 | REINSTALL #4 DOOR G4 GLY R/H AISLE S/W ARED PANEL BUMPER AND ATTACH PARTS | VT | L347 | 2 | AI
2C | 5 | REINSTALL #4 DOOR G4 GLY R/H AISLE S/W ARED PANEL PROXIMITY LIGHT | VT | L347 | 1 | AV
1C | 1 | REPLACE THE BONDING JUMPER | VT | L359 | 2 | AE
1C | 2 | C/OUT THE BONDING TEST | VT | L359 | 1 | AV
1C | 1 | REMOVE S1-01 COMPT DOOR BUMPER AND ATTACH PART | VT | L368 | 2 | AI
1C | 2 | CAB S1-01COMPT DOOR TEDLAR REPLACE | VT | L368 | 6 | SS
1C | 3 | CAB S1-01 COMPT DOOR ATTACH PARTS | VT | L368 | 2 | AI
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L374 | 16 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L374 | 8 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L374 | 0.01 | PT
1C | 1 | REMOVE THE FUEL TANK PNL - 633FB, FOR ACC. | VT | L379 | 1 | AE
1C | 2 | RE-INSTALL THE FUEL TANK PNL - 633FB. | VT | L379 | 1.5 | AE
1C | 3 | REMOVE THE FUEL MEASURE STICK MOUNTING BASE. | VT | L379 | 1.5 | SM
1C | 4 | RE-INSTALL THE FUEL MEASURE STICK MOUNTING BASE. | VT | L379 | 1.5 | SM
2C | 5 | APPLY THE CAP SEAL AND FILLET SEAL TO THE BOLTS, WASHER, COLLAR AND MOUNTING BASE. | VT | L379 | 1 | AE
2C | 6 | MEASURE THE BONDING RESISTANCE BETWEEN THE MOUNTING BASE AND THE ACCESS DOOR, MAKE SURE THE BONDING RESISTANCE IS 0.001 OHM (1 MILLIOHM) OR LESS. | VT | L379 | 1 | AV
2C | 7 | PERFORM FUEL LEAK CHECK AT THE PNL - 633FB. | VT | L379 | 0.5 | AE
1C | 1 | PLS DISCONNECT ELECTRICAL CONNECTOR REF | VT | L380 | 1 | AV
1C | 2 | REMOVE EDP REF | VT | L380 | 8 | AE
1C | 3 | INSTALL EDP REF | VT | L380 | 12 | AE
1C | 4 | REINSTALL ELECTRICAL CONNECTOR REF | VT | L380 | 2 | AV
2C | 5 | PERFORM ENG RUN EDP INSTALLATION TEST REF | VT | L380 | 1 | AE
2C | 6 | PERFORM DRY MOTOR LEAK CHK REF | VT | L380 | 1 | AE
2C | 7 | PERFORM IDLE LEAK CHK REF | VT | L380 | 1 | AE
2C | 8 | PERFORM PART POWER LEAK CHK REF | VT | L380 | 1 | AE
1C | 1 | REPLACED BROKEN ANCHOR NUTS | VT | L450 | 2 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L450 | 1 | PT
1C | 1 | INSTALL THE ACC PNL FOR PT PAINTING | VT | L452 | 1 | AE
1C | 2 | REMOVE THE ACC PNL | VT | L452 | 1 | AE
1C | 3 | INSTALL THE ACC PNL | VT | L452 | 1 | AE
1C | 1 | INSTALL THE ACC PNLS | VT | L454 | 2 | AE
1C | 2 | REMOVE THE ACC PNLS | VT | L454 | 2 | AE
1C | 3 | INSTALL THE ACC PNLS | VT | L454 | 2 | AE
1C | 1 | REPLACED DAMAGE STAND OFFS | VT | L482 | 4 | SM
1C | 2 | REMOVE WIRE | VT | L482 | 0.5 | AV
1C | 3 | INSTALL WIRE | VT | L482 | 1 | AV
1C | 4 | TOUCH UP TOP COAT | VT | L482 | 1 | PT
1C | 1 | REPLACED DAMAGE ANCHOR NUTS | VT | L484 | 4 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L484 | 1 | PT
1C | 1 | PLS REMOVE THE OGV EXTENSION PNLS REF | VT | L501 | 4 | AE
1C | 2 | INSTALL THE L/H UPPER OGV EXTENSION PNL REF | VT | L501 | 5 | AE
2C | 3 | INSTALL THE NEW ANCHOR NUT | VT | L501 | 3 | SM
1C | 1 | REMOVE #5 DOOR CREW REST AFT AREA PANEL BUMPER AND ATTACH PARTS | VT | L512 | 1 | AI
1C | 2 | REMOVE #5 DOOR CREW REST AFT AREA PANEL PROXIMITY LIGHT PARTS | VT | L512 | 1 | AV
1C | 3 | CAB #5 DOOR CREW REST AFT AREA PANEL TEDLAR REPLACE | VT | L512 | 12 | SS
1C | 4 | REINSTALL #5 DOOR CREW REST AFT AREA PANEL BUMPER AND ATTACH PARTS | VT | L512 | 1 | AI
2C | 5 | REINSTALL #5 DOOR CREW REST AFT AREA PANEL PROXIMITY LIGHT PARTS | VT | L512 | 1 | AV
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L525 | 20 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L525 | 14 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L525 | 0.01 | PT
1C | 1 | REPLACED DAMAGE ANCHOR NUTS | VT | L526 | 7 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L526 | 1 | PT
1C | 1 | REPLACED DAMAGE ANCHOR NUT | VT | L527 | 10 | SM
1C | 2 | TOUCH UP TOP COAT | VT | L527 | 1 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L528 | 2 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L528 | 2 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L528 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L529 | 2 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L529 | 2 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L529 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L531 | 20 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L531 | 14 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L531 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L536 | 10 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L536 | 10 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L536 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L537 | 10 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L537 | 10 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L537 | 0.01 | PT
1C | 1 | REPLACE THE BONDING JUMPER | VT | L554 | 2 | AE
1C | 2 | PLS CARRY OUT JUMPER RESISTANCE TEST | VT | L554 | 0.5 | AV
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L561 | 2 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L561 | 2 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L561 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L562 | 2 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L562 | 1 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L562 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L563 | 2 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L563 | 2 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L563 | 0.01 | PT
1C | 1 | APPLY THE RESIN COATING TO IRREGULAR AREA | VT | L564 | 2 | SS
1C | 2 | SAND THE RESIN COATING TO MAKE SURFACE SMOOTHER | VT | L564 | 1 | SS
1C | 3 | APPLY THE SURFACE PAINT | VT | L564 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L565 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA | VT | L565 | 20 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L565 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L565 | 3 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L565 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L565 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L565 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L565 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L566 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA(2EA) | VT | L566 | 12 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L566 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L566 | 2 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L566 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L566 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L566 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L566 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L567 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA(2EA) | VT | L567 | 12 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L567 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L567 | 2 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L567 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L567 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L567 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L567 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L568 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA(2EA) | VT | L568 | 12 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L568 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L568 | 2 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L568 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L568 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L568 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L568 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L569 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA(2EA) | VT | L569 | 20 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L569 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L569 | 3 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L569 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L569 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L569 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L569 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L570 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA(2EA) | VT | L570 | 12 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L570 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L570 | 2 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L570 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L570 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L570 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L570 | 0.01 | PT
1C | 1 | DO AN INSPECTION TO FIND THE DAMAGE DIMENSION | VT | L571 | 1 | NT
1C | 2 | DO THE REPAIR TO DAMAGED AREA(2EA) | VT | L571 | 12 | SS
1C | 3 | DO THE POST REPAIR INSPECTION | VT | L571 | 1 | NT
1C | 4 | APPLY RESIN AND SMOOTH OUT | VT | L571 | 2 | SS
2C | 5 | FILL IN THE SDR FORM | VT | L571 | 0.01 | SS
2C | 6 | APPLY CONDUCTIVE COATING | VT | L571 | 1 | PT
2C | 7 | MEASURE THE RESISTIVITY OF CONDUCTIVE COATING | VT | L571 | 0.5 | AV
2C | 8 | RESTORE SURFACE FINISH | VT | L571 | 0.01 | PT
1C | 1 | REPLACED THE STAND OFF | VT | L581 | 2 | SM
1C | 2 | REMOVE WIRE | VT | L581 | 0.5 | AV
1C | 3 | REINSTALL WIRE | VT | L581 | 1 | AV
1C | 4 | TOUCH UP TOP COAT | VT | L581 | 1 | PT

## MHR
TOTAL
4318.35